# VENUEVUE PROJECT PLAN

## Document Revision 2.3 — Final Architecture-Reconciled & Audit-Aligned Baseline

Project Title: VenueVue: An Internet-Independent, Locally Networked Point-of-Sale and Recipe-Driven Inventory Management System for Mobile Pop-Up Coffee Shops

Industry Client: TRAVELBEAN MNL — Pampanga St., Tondo, Manila

Development Team: CTRL + STAY

Academic Programme: COSC 75: Software Engineering II

Institution: Cavite State University — College of Engineering and Information Technology (CEIT), Department of Computer Studies / Information Technology, Don Severino delas Alas Campus, Indang, Cavite

Date of Issue: 23 September 2026

Status: Approved Baseline — Frozen for Implementation

Academic Window: 3 August 2026 – 18 December 2026 (19.5 Weeks)

## TABLE OF CONTENTS

| Section | Title |
| --- | --- |
| 1 | Project Charter & Administrative Baseline |
| 1.1 | Document Control & Revision Lineage |
| 1.2 | Project Summary & Objectives |
| 1.3 | Stakeholders, Team Roles & RACI Matrix |
| 2 | System Architecture & Technical Specifications |
| 2.1 | Architecture Overview |
| 2.2 | Operational Availability & Cloud Exclusion (ADR-001) |
| 2.3 | Three Data Ingestion Mechanisms |
| 3 | Database Architecture (9-Table Core Schema) |
| 3.1 | Data Model Rationale |
| 3.2 | Production SQL DDL Script |
| 4 | API & Transactional Specifications |
| 4.1 | Order Ingestion Contract & JSON Envelope |
| 4.2 | Production API Engine (sync.php) |
| 5 | Work Breakdown Structure & 10-Sprint Roadmap |
| 5.1 | Sprint Schedule Table |
| 5.2 | Feature Freeze & Critical Path |
| 6 | Risk Management, Compliance & Legal Alignment |
| 6.1 | Critical Risk Assessment & Mitigation Matrix |
| 6.2 | Legal & Contractual Alignments |
| 7 | Appendices |
| 7.1 | Appendix I — ADR-001 Architecture Decision Record |
| 7.2 | Appendix II — Addendum A: Clarification of Team Role Designations |

## DISCLAIMER

This Project Plan is submitted to the College of Engineering and Information Technology (CEIT), Cavite State University — Don Severino delas Alas Campus, Indang, Cavite, in partial fulfilment of the requirements for COSC 75: Software Engineering II. It is the original work of the authors, except where references are explicitly cited.

The content of this document, including but not limited to the report, source code, database schema, and related materials, may be used, copied, or distributed for academic and research purposes, provided that proper acknowledgment is given to the authors and Cavite State University. Unauthorized use for commercial purposes without prior consent is strictly prohibited.

## ABSTRACT

Mobile pop-up coffee vendors operate in dynamic physical environments where permanent internet connectivity is absent or prohibitively unstable. TravelBean MNL, a mobile coffee venture based in Pampanga St., Tondo, Manila, established in 2024, faces severe operational bottlenecks arising from manual paper-based order taking, post-event calculator sales tallying, and unmonitored raw-material consumption. Existing commercial point-of-sale (POS) systems either depend strictly on cloud infrastructure — rendering them unusable in cellular dead zones — or fail to track inventory at the ingredient level, deducting finished units rather than the raw materials (espresso beans in grams, full-cream milk in millilitres, cups in units) that a specialty coffee recipe actually consumes.

VenueVue, engineered by group CTRL + STAY, is an internet-independent Point-of-Sale and recipe-driven Inventory Management System designed specifically to eliminate these operational gaps. The system is built around a local edge client-server model: a host laptop running an offline XAMPP stack (Apache, PHP 8.x, MySQL 8.x with InnoDB) broadcasts a local Wi-Fi hotspot on the 192.168.137.x subnet. Barista and administrative tablets connect to this local network through standard web browsers, executing a touch-optimised React 19 Single Page Application. The system performs real-time order processing, atomic recipe-based ingredient deduction under row-level locking, and immediate low-stock threshold alerting, all without any WAN/Internet dependency. Client-side durability during network partitions is provided by an IndexedDB transaction queue with UUIDv4 idempotency enforcement; post-event reconciliation is supported through structured USB recovery packages and PhpSpreadsheet-based Excel/CSV batch ingestion. Reporting is delivered through automated four-tab .xlsx workbooks generated by the PhpSpreadsheet library.

This Project Plan documents the complete software development lifecycle for VenueVue across a 19.5-week (137-day) academic timeline running from 3 August 2026 to 18 December 2026, structured as ten two-week Agile delivery sprints bounded by Waterfall governance gates. It establishes the frozen nine-table relational schema, the API-level security and transactional specification, the rebalanced RACI responsibility assignment matrix with mandatory independent verification, the risk register, and the critical-path schedule culminating in a 27 November 2026 feature freeze and three weeks of reserved verification, training, and User Acceptance Testing.

# SECTION 1 — PROJECT CHARTER & ADMINISTRATIVE BASELINE

## 1.1 Document Control & Revision Lineage

### 1.1.1 Purpose of Document Control

This section establishes formal configuration control over the Project Plan and its revision history. The Project Plan functions as the governing management instrument for the VenueVue engagement: it is developed during project initiation, remains stable throughout the project life cycle, and serves as an ongoing reference for all project stakeholders. Any modification to scope, architecture, schedule, or responsibility assignment must be recorded in the Revision Lineage table below and re-approved by the Project Manager, the System Analyst, and the Industry Client.

### 1.1.2 Current Baseline Declaration

Document Revision 2.3 is hereby declared the single frozen baseline for the VenueVue project.

Revision 2.3 explicitly and completely supersedes the following historical revisions, all of which are withdrawn from use for any purpose including submission, defence, or implementation:

•  Rev 1.0 (28 August 2026) — initial SE II baseline draft

•  Rev 1.1 (10 September 2026) — six-table ERD update

•  Rev 1.2 (22 September 2026) — Phase 1 milestone and calendar alignment

•  Rev 2.0 (22 September 2026) — technology stack pivot record

•  Rev 2.1 (23 September 2026) — architecture-aligned reconciliation

•  Rev 2.2 (23 September 2026) — reconciled baseline and specification freeze

•  Rev 3.0 (9 May 2026) — Software Engineering I comprehensive plan

Revision 2.3 was produced following a comprehensive audit of all fourteen project documents and both source-code trees then in existence. That audit identified critical architectural divergences, a non-functional ingest contract, a schema incapable of producing the client's primary contractual report, an unimplemented reporting module, absent API security controls, contradictory role assignments between the signed Letter of Agreement and the plan, a non-monotonic version lineage, and a schedule containing zero float. Revision 2.3 resolves every finding and constitutes the authoritative specification for Phase 3 onward.

### 1.1.3 Revision Lineage — Software Engineering II Lineage (Governing)

| Revision | Date of Issue | Author(s) | Brief Description of Change |
| --- | --- | --- | --- |
| 1.0 | 28 August 2026 | Zapico, Zaki | Initial Software Engineering II baseline project plan draft. |
| 1.1 | 10 September 2026 | Gregorio, Rhea Mae | Entity-Relationship Diagram updated to a six-table schema; local star network topology specifications added. |
| 1.2 | 22 September 2026 | Zapico, Zaki | Phase 1 completion milestone integrated; academic calendar alignment to 3 August – 18 December 2026; PhpSpreadsheet export specifications; multi-protocol offline data sync details introduced. |
| 2.0 | 22 September 2026 | Zapico, Zaki | Technology stack and multi-tablet architecture upgrade: front-end transformed from native mobile builds to a React 19 + TanStack Router/Start Single Page Application compiled via Vite 8 and styled with Tailwind CSS 4; PWA/Kiosk WebView container execution incorporated; Mobile Admin Tablet Console topology added. |
| 2.1 | 23 September 2026 | Zapico, Zaki | Architecture-aligned reconciliation. Eight-table schema introduced (adding INVENTORY_TRANSACTIONS and AUDIT_LOGS); UUIDv4 idempotency engine; atomic InnoDB row-locking; fourteen-scenario experimental test matrix; standardised architectural terminology dictionary. Front matter, functional requirements, role assignments, deliverables register, and references omitted in this revision. |
| 2.2 | 23 September 2026 | Zapico, Zaki | Reconciled Baseline and Specification Freeze; eight-table schema frozen; three data-ingestion mechanisms formally renamed and defined. |
| 2.3 | 23 September 2026 | Zapico, Zaki (Project Manager / Lead Developer) | FINAL ARCHITECTURE-RECONCILED & AUDIT-ALIGNED BASELINE — CURRENT. Ratifies ADR-001 (React 19 SPA + PHP 8.x / MySQL 8.x on XAMPP; Flutter retired to archive; hosted cloud services excluded). Expands the core schema from eight to nine tables (EVENTS, ORDERS.event_id, ORDERS.payment_method, INGREDIENTS.unit_cost) to enable the contractually specified per-event and net-profit reporting. Restores the functional and non-functional requirements baseline, deliverables register, role assignments, RACI matrix, client stakeholder register, references, and document change control removed in Rev 2.1. Corrects the historical technology-pivot narrative. Corrects the overstated 20-week duration to the measured 19.5 weeks. Rebalances task ownership and mandates independent verification such that no team member is the sole author and sole verifier of any deliverable. Replaces all Flutter/SQLite client specifications with the ratified React 19 / IndexedDB client specification. Supersedes Rev 1.0, 1.1, 1.2, 2.0, 2.1, 2.2, and Rev 3.0 in their entirety. |

### 1.1.4 Revision Lineage — Software Engineering I Lineage (Historical, Superseded)

The following revisions originated in the preceding Software Engineering I course and are retained for academic continuity only. They do not govern the current implementation.

| Revision | Date of Issue | Author(s) | Brief Description of Change |
| --- | --- | --- | --- |
| 0.1 | 26 April 2026 | Zapico, Zaki | Initial problem-domain investigation and SWOT identification. |
| 1.0 | 3 May 2026 | Roquid, Jenny Lyn | Prioritised SWOT matrix and problem scoring integrated. |
| 1.5 | 8 May 2026 | Gregorio, Rhea Mae | Fishbone problem stratification and preliminary ERD. |
| 2.0 | 9 May 2026 | Zapico, Zaki | Project Technical Documentation consolidated. |
| 3.0 | 9 May 2026 | Zapico, Zaki | Five-Month Comprehensive Plan expanded to 20 weeks for document conversion. |

Note on historical accuracy. Revision 2.0 of the governing lineage asserted that "native mobile builds (such as Flutter APKs) were evaluated during early planning." This claim is not supported by the earliest artefact. The Software Engineering I plan (Rev 3.0, 9 May 2026) contains no reference to Flutter and selected a browser-delivered HTML5/CSS3/JavaScript client. The accurate historical sequence — recorded in Appendix I, ADR-001, and applied throughout this document — is that the project's initial architecture was a browser-delivered HTML/CSS/JavaScript client, that native Flutter APK deployment was evaluated and rejected during Rev 2.0 planning for the operational reasons stated therein, and that a React 19 Single Page Application was selected in its place. Revision 2.3 corrects this record.

### 1.1.5 Superseded Artefacts Withdrawn from Submission

The following files remain in the working environment but are withdrawn from the submission pack and must not be presented to the panel or the client:

| Artefact | Reason for Withdrawal |
| --- | --- |
| 4. PROJECT PLAN.docx.pdf | Blank Cavite State University template containing no project content. |
| 7. SAMPLE LETTER OF AGREEMENT.docx | Unadapted barangay letter-of-agreement template describing barangay residents' records and barangay-issued documents; unrelated to this project. |
| Venue Vue Sample Agreement portrait.pdf | Byte-identical duplicate of Venue Vue Sample Agreement.pdf; re-layout only. |
| Act as the Project Manager (Zapico, Zaki) of grou....docx | Byte-identical duplicate of VENUEVUE SYSTEM ARCHITECTURE & TECHNICAL SPECIFICATIONS.docx. |
| you should revised this based on the neeede to re....docx | Byte-identical duplicate of Project Plan 2.0.docx; a prompt-named file that has been overwritten by its own output. |
| Project Plan 2.0.docx / Project Plan 2.0 (1).docx | Superseded revisions (Rev 2.1 and Rev 2.0 respectively; filenames are inconsistent with their internal revision numbers). |
| VenueVue Software Project Plan FIrst.docx | Software Engineering I artefact; contains blanket pre-dated approvals. |
| CTRL Stay coding/, VenueVue/flutevue/ | Flutter prototype source trees retired by ADR-001; retained only under archive/flutter-prototype. |

## 1.2 Project Summary & Objectives

### 1.2.1 System Overview

VenueVue is an internet-independent, locally networked, offline-first Point-of-Sale and recipe-driven Inventory Management System custom-engineered for mobile pop-up coffee shop operations. It is deployed as a local edge client-server system consisting of three tiers operating entirely within a self-contained wireless star topology broadcast by a host laptop — no external router, no internet service provider, and no hosted cloud service participates in transaction processing.

The system exists to resolve a specific and well-evidenced operational failure. TravelBean MNL operates a motorcycle-based mobile pop-up coffee venture serving specialty espresso drinks, cold brew, flavour-infused beverages, and light pastries at catering events, school fairs, weddings, and private parties throughout Metro Manila and nearby provinces. Because event venues frequently operate in cellular dead zones or congested wireless environments, any POS system whose operation depends upon cloud connectivity fails precisely when the business needs it most. Simultaneously, standard retail POS software tracks inventory as discrete finished units — selling one canned beverage deducts exactly one unit — and is therefore structurally incapable of modelling a specialty coffee recipe, in which preparing a single 16oz Iced Salted Caramel Latte simultaneously consumes 18 grams of espresso beans, 200 millilitres of full-cream milk, 30 millilitres of salted caramel syrup, one 16oz clear plastic cup, one dome lid, and one plastic straw.

VenueVue bridges both gaps. The host laptop operates an offline XAMPP stack — Apache, PHP 8.x, and MySQL 8.x on the InnoDB engine — and broadcasts a Windows Mobile Hotspot on the 192.168.137.x subnet, statically claiming 192.168.137.1. Barista and administrative tablets connect to that hotspot and access a touch-optimised React 19 Single Page Application through Google Chrome or Apple Safari, requiring no application installation and no per-device build management. Completed orders are transmitted over the local network to a PHP 8.x API, which resolves prices server-side, executes atomic multi-ingredient recipe deductions under SELECT … FOR UPDATE row-level locking, writes an append-only inventory movement ledger and security audit trail, and commits the transaction under InnoDB ACID guarantees. A UUIDv4 client_transaction_id generated on the client and protected by a database UNIQUE constraint guarantees exactly-once ingestion. When the local network or host is unavailable, the client queues transactions in IndexedDB under a PENDING_LOCAL state and reconciles them on recovery. Post-event reporting is automated through the PhpSpreadsheet library, which compiles a four-tab Excel workbook — Summary, Sales by Product, Ingredient Usage, and Restock List — in under ten seconds, replacing two to three hours of late-night manual calculation per event.

### 1.2.2 Statement of the Problem

A quantitative SWOT and problem-prioritisation analysis conducted by group CTRL + STAY with TravelBean MNL identified seven core operational problems, ranked by urgency, productivity impact, familiarity, solvability, and implementability on a scale of zero to ten:

| Priority Rank | Problem Identification | Operational Impact | Current Client Workaround | Priority Score |
| --- | --- | --- | --- | --- |
| 1 | Total absence of an internet-independent POS system | Forces paper-based order entry, producing miscalculated totals and lost order slips. | Writing orders on physical notepads. | 43 |
| 2 | Manual post-event sales tallying | Requires two to three hours of manual calculation per event, causing operator burnout. | Tallying paper receipts using handheld calculators. | 42 |
| 3 | Inefficient product and ingredient inventory tracking | Frequent mid-event stockouts of essential items such as espresso beans, full-cream milk, and cups. | Visual estimation and post-event manual updates to basic Excel sheets. | 38 |
| 4 | Absence of low-stock alert notifications | Staff remain unaware when raw materials reach critical thresholds, causing rejected customer orders. | Manual spot checks during event lulls. | 34 |
| 5 | Lack of historical event performance data | Management cannot identify best-selling products, peak hours, or high-margin events. | Reliance on intuition and memory. | N/A |
| 6 | Time-consuming administrative reconciliation | Labour fatigue reduces overall operational efficiency and constrains business scalability. | Owners working long unpaid hours after events. | N/A |
| 7 | Severe manpower constraints | A small three-member team is forced to divide attention between customer service and manual paperwork. | Operations Manager personally handling manual logging during sales. | N/A |

Root-cause stratification. Operational breakdowns propagate sequentially throughout the business structure. The absence of a dedicated POS system leads directly to manual tracking of orders, which in turn creates a total lack of historical sales data from past events. In parallel, inefficient ingredient tracking causes unexpected stockouts, resulting in unrecorded waste and lost revenue. Operating without a permanent brick-and-mortar storefront forces full reliance on catering events, magnifying transportation and operational overhead. When combined with a small operational team handling multiple physical roles, manual administrative tasks severely impair customer service delivery and cause worker burnout.

Critical scope consequence. Problem Rank 5 — the absence of historical event performance data — cannot be solved by a data model that contains no concept of an event. The audit of predecessor revisions established that neither the six-table nor the eight-table schema contained an EVENTS entity, an ORDERS.event_id association, or any ingredient cost field, and that the contractually specified Tab 1 of the reporting workbook nevertheless requires "Event Name, Date, Duration, Total Gross Revenue, Net Profit Estimates, … Primary Payment Distribution." Revision 2.3 therefore expands the core schema to nine tables. This is not optional enrichment; it is the minimum structural change required to satisfy the client's ranked business requirement and the contractual reporting specification.

### 1.2.3 Quantifiable Objectives and Success Metrics

The general objective of group CTRL + STAY is to design, develop, test, and deploy VenueVue, an internet-independent Point-of-Sale and recipe-driven Inventory Management System that automates order processing, sales tracking, ingredient-level inventory deduction, low-stock threshold alerting, per-event profitability analysis, and post-event analytical report generation for TravelBean MNL.

The general objective is decomposed into eight specific, measurable objectives. Each is bound to an explicit target metric and acceptance criterion so that project success is objectively verifiable rather than subjectively asserted.

| # | Specific Objective | Target Metric / Formula | Baseline / Target Criterion |
| --- | --- | --- | --- |
| 1 | Digitally capture customer transactions at the point of sale. | Paper Order Elimination Rate | 100% elimination of paper order slips during event operations. |
| 2 | Automate raw material inventory deductions based on product recipes. | Recipe Deduction Accuracy (A_deduction) | A_deduction = 100.00% agreement between theoretical bill-of-materials depletion and recorded database updates. |
| 3 | Implement real-time low-stock alerting mechanisms. | Visual Alert Trigger Accuracy | Alerts render immediately whenever Q_hand ≤ Q_threshold. |
| 4 | Guarantee internet-independent system availability during mobile events. | WAN-Partitioned Functional Availability | 100% operational availability with zero WAN/Internet connectivity, provided the local host and LAN remain active. |
| 5 | Automate post-event sales and operational report generation. | Export Latency (T_export) | Four-tab .xlsx workbook generated in T_export ≤ 10 seconds post-event. |
| 6 | Enable flexible multi-mechanism data ingestion with exactly-once semantics. | Offline Reconciliation Rate (R_sync) and Duplicate Creation Rate (R_duplicate) | R_sync = 100%; R_duplicate = 0%. |
| 7 | Enforce API-level Role-Based Access Control across all devices. | API Authorization Enforcement Rate | Strict backend HTTP 401/403 rejection of every unauthorized API call, with every rejection logged. |
| 8 | Produce per-event profitability analytics. | Event Profitability Coverage | Tab 1 of the workbook reports event name, date, duration, gross revenue, cost of goods sold, and net profit for 100% of closed events; a closed event with no associated orders reports explicit zero values rather than being omitted. |

Formal metric definitions. The following formulae govern experimental evaluation and are referenced throughout this plan.

Recipe Deduction Accuracy measures absolute precision between calculated mathematical stock depletion (Q_BOM) and physical database updates (Q_DB) across $n$ evaluation observations:

A_deduction = ( 1 - (Σ_i=1^n|Q_BOM,i-Q_DB,i|)/(Σ_i=1^n|Q_BOM,i|) ) × 100%

End-to-End Transaction Latency measures turnaround time between client transmission (t_submit) and server database confirmation (t_commit), with the 95th percentile computed across all observations:

L_trans,j = t_commit,j - t_submit,j L_mean = (1)/(n)Σ_j=1^n L_trans,j

Offline Reconciliation Rate and Duplicate Creation Rate evaluate data restoration completeness following a network partition in which N_queued transactions were queued locally:

R_sync = (N_reconciled)/(N_queued) × 100% R_duplicate = (N_duplicate)/(N_queued) × 100%

Transaction Success Rate and Throughput characterise sustained load behaviour:

R_success = (N_successful)/(N_attempted) × 100% T = (N_committed)/(Δ t)

### 1.2.4 Requirements Baseline

Revision 2.1 removed the functional and non-functional requirement definitions entirely while simultaneously adding substantial engineering complexity — UUIDv4 idempotency, an IndexedDB queue, row-level locking, and a fourteen-scenario test matrix — none of which traced to any stated requirement. Revision 2.3 restores and extends the requirements baseline so that every engineered capability is traceable to a numbered requirement.

Functional Requirements

| ID | Requirement | Traces To Objective |
| --- | --- | --- |
| FR-01 | The User Authentication module must enforce credential-based login with API-level, server-side role validation, directing authenticated users to barista or owner interfaces and rejecting unauthorized API calls with HTTP 401 or HTTP 403. | 7 |
| FR-02 | The POS Touch Order Entry module must render products in category tabs and permit single-tap item selection, with cart adjustment and cash change calculation. | 1 |
| FR-03 | The Payment module must accept cash tender and automatically compute change due, with unit prices resolved exclusively from the server-side product table and never accepted from the client. | 1 |
| FR-04 | The Inventory Engine must deduct raw ingredients automatically and atomically based on mapped product recipes upon order completion, writing one movement-ledger row per ingredient affected. | 2 |
| FR-05 | The Alerting Engine must display visual low-stock warnings whenever an ingredient's current stock falls to or below its configured minimum threshold, and must expose a restock list. | 3 |
| FR-06 | The Data Ingestion module must support order capture via real-time local Wi-Fi HTTP POST, IndexedDB queue recovery over USB, and manual Excel/CSV batch ingestion, with UUIDv4 idempotency guaranteeing exactly-once commit. | 4, 6 |
| FR-07 | The Reporting module must export four-tab Excel workbooks (Summary, Sales by Product, Ingredient Usage, Restock List) generated by the PhpSpreadsheet library. | 5 |
| FR-08 | The Event Analytics module must associate every order with an event record and compute per-event gross revenue, cost of goods sold, and net profit, and must report event name, date, duration, and payment distribution. | 8 |
| FR-09 | The Master Data module must provide create, read, update, and deactivate operations for products, ingredients, events, and recipe mappings, restricted to the Owner role. | 2, 5, 8 |

Non-Functional Requirements

| ID | Requirement | Target | Notes |
| --- | --- | --- | --- |
| NFR-01 | Offline Availability | 100% functional availability absent WAN/Internet connectivity, provided the local host and LAN remain active. | Restored from Rev 1.0; reinforced by ADR-001 cloud exclusion. |
| NFR-02 | UI Touch Responsiveness | Touch interaction response time under 200 milliseconds. | Restored from Rev 1.0; deleted without replacement in Rev 1.1. |
| NFR-03 | Security | Passwords hashed with password_hash(); all database access via PDO prepared statements; API-level RBAC enforced server-side. | Aligned to Letter of Agreement §5.1. |
| NFR-04 | Backup and Recovery | Automated daily .sql database dump on the host laptop, mirrored to an external USB drive. | Restored from Rev 1.0 and Letter of Agreement §1.3; deleted in Rev 2.1. |
| NFR-05 | Data Integrity | Full ACID compliance; atomic order, deduction, and ledger writes within a single transaction; zero lost updates under concurrent multi-tablet submission. | Enforced by InnoDB and SELECT … FOR UPDATE. |
| NFR-06 | Export Performance | Four-tab workbook generated within 10 seconds of request. | Traces to Objective 5. |
| NFR-07 | Auditability | Append-only inventory movement ledger and append-only security audit log; no destructive mutation of historical records. | Enforced by design of inventory_transactions and audit_logs. |
| NFR-08 | Client Portability | Operation on any Android 8.0+ tablet or iPadOS 14+ iPad using a current Chrome or Safari browser, with no application installation required. | Justifies ADR-001 client-tier selection. |

Client-Side Transaction Validation Rules. The following rules are enforced on the client before transmission, and re-validated authoritatively on the server:

1. Orders containing zero line items are rejected outright.

2. Item quantities must be positive integers greater than zero. Negative and zero quantities are rejected explicitly; the server must not rely on truthiness testing, since a negative value is truthy in PHP and was previously accepted, producing a negative deduction that increased recorded stock.

3. Unit prices are locked to internal system menu tables and cannot be manually overridden by baristas.

4. Each order receives a client-generated UUIDv4 client_transaction_id before first transmission. This identifier is the sole idempotency key. Truncated, hashed-timestamp, or sequential identifiers are prohibited.

5. Every order is associated with a tablet_id and, where an event is active, an event_id.

### 1.2.5 Formal Deliverables Register

Group CTRL + STAY shall deliver the following formal documentation and software artefacts upon project completion. The present status column reflects the audited position as of 23 September 2026 and is retained in this baseline to make completion measurable.

| # | Deliverable | Format / Medium | Description / Specification | Status at Rev 2.3 |
| --- | --- | --- | --- | --- |
| 1 | Project Plan and Project Charter | PDF / DOCX | Comprehensive operational and managerial project plan; this document. | Complete |
| 2 | Software Requirements Specification (SRS) | PDF / DOCX | Numbered functional and non-functional requirements with traceability matrix. | Pending — Sprint 5 |
| 3 | Prioritised SWOT Analysis and Fishbone Report | PDF / DOCX | Prioritised SWOT matrix, fishbone diagram, and problem ranking. | Complete |
| 4 | Reconciled Project Technical Documentation and System Architecture Diagrams | PDF / DOCX | Technical specifications, network topology, and hardware specification. | Complete |
| 5 | Database ERD and DDL Schema Scripts | SQL / PDF | Entity-Relationship Diagram with complete attribute data types, and executable DDL for the nine-table core schema. | Partial — 9-table DDL specified in §3.2; visual ERD pending |
| 6 | Figma Interactive Touch UI Wireframes | Figma Link / PDF | Interactive wireframes covering seven core system screen layouts. | Pending — Sprint 4 |
| 7 | VenueVue SPA and API Source Code | React 19 / Vite 8 / Tailwind CSS 4 / PHP 8.x / MySQL 8.x | Fully functional source code deployed within the XAMPP environment. | In Progress |
| 8 | PhpSpreadsheet Automated Four-Tab Excel Workbook Templates | .xlsx | Pre-formatted, four-tab structured financial and stock report layouts. | Pending — Sprints 8 |
| 9 | User Operational Manual and System Installation Guide | PDF | Concise operational guide for baristas and owners, and step-by-step setup guide covering XAMPP, MySQL, and hotspot configuration. | Pending — Sprints 9–10 |
| 10 | Comprehensive Test Plan, Execution Logs, and Signed UAT Acceptance Certificate | PDF / DOCX | Completed test scripts covering scenarios T01–T14, execution logs, defect register, and signed acceptance documentation. | Pending — Sprints 5, 9, 10 |

## 1.3 Stakeholders, Team Roles & RACI Matrix

### 1.3.1 Industry Client Stakeholder Register

| Stakeholder | Position / Designation | Role in the Engagement |
| --- | --- | --- |
| Rhona Mae Aganan | Owner & Operations Manager | Primary client authority and approver. Directly performs order taking, customer service, administrative reporting, and inventory management. Responsible for baseline operational data provision and User Acceptance Testing sign-off. |
| Jimwell Mamangun | Co-Owner & Logistics Manager | Secondary client authority. Handles equipment transportation, site setup, stock procurement, and physical logistics. Responsible for provision of hardware and event-site access. |
| Hired Barista | Beverage Preparation Staff | Primary end-user of the POS interface. Focused on espresso extraction, beverage preparation, and order fulfilment. Participates in usability testing and training. |
| Academic Instructor / Evaluator | Faculty, Department of Computer Studies / Information Technology, CEIT | Academic assessor. Reviews documentation, witnesses defence, and evaluates conformance to Software Engineering II requirements. |
| Faculty Adviser / Project Representative | Department of Computer Studies / Information Technology, CEIT | Academic endorser of the Letter of Agreement and project governance. |

Client operational profile. TravelBean MNL is a three-person mobile pop-up coffee operation established in 2024, operating a specialised motorcycle setup from Pampanga St., Tondo, Manila. The business is cash-only and operates on a single-event basis, which bounds the system's payment and multi-tenancy scope. Hardware — the server laptop and barista tablets — is supplied directly by the client.

### 1.3.2 Development Team Composition and Role Designations

The software engineering team CTRL + STAY consists of three undergraduate developers from Cavite State University. The role designations below are authoritative for all purposes, including the Letter of Agreement, and are formally reconciled with the signed Agreement by Addendum A (Appendix II, §7.2).

| Personnel | Academic / Project Role | Primary Project Responsibilities |
| --- | --- | --- |
| Zapico, Zaki | Project Manager / Lead Developer | Overall project governance and timeline tracking; client requirements alignment; SWOT prioritisation and risk management; ADR authorship and architecture ratification; network topology specification; database schema design and execution; PHP 8.x backend and API engine development; React 19 SPA client architecture; PhpSpreadsheet export integration support; deployment and hotspot configuration; post-turnover support. |
| Gregorio, Rhea Mae | System Analyst / QA Lead | Requirements gathering and Software Requirements Specification authorship; use-case modelling; Entity-Relationship Diagram and schema design; System Architecture modelling and technical documentation; test strategy creation and test-plan authorship; QA oversight and quality-gate sign-off; master-data CRUD implementation; Figma touch UI wireframing; user operational manual and installation guide authorship; integration defect resolution. |
| Roquid, Jenny Lyn | QA & Testing Specialist | Test script execution across scenarios T01–T14; unit and integration testing; network partition and fail-safe validation; offline reconciliation verification; PhpSpreadsheet export validation; low-stock alerting module implementation; CSV/USB ingestion verification; IndexedDB quota handling implementation; bug logging and defect tracking; usability assessment; User Acceptance Testing execution; barista and owner training delivery. |

Independent verification mandate. No member of CTRL + STAY shall be the sole author and sole verifier of the same deliverable. Every artefact enumerated in §1.2.5 must carry, at minimum, one named verifier who did not author it. This rule responds directly to the audited condition in which a single member both constructed and validated the low-stock alerting and PhpSpreadsheet export modules, and in which the System Analyst both authored and self-signed as reviewer of the same document. Compliance is enforced at each quality gate defined in §5.1.

### 1.3.3 RACI Responsibility Assignment Matrix

The distribution of responsibilities across the project life cycle is governed by the RACI framework. The following key applies: R = Responsible (performs the work); A = Accountable (owns the outcome and bears final authority; exactly one per row); C = Consulted (provides input before the work is finalised); I = Informed (notified of outcome).

Because this project mandates independent verification, a discrete Independent Verifier column is appended. The verifier is always a member other than the row's Responsible party, and verification is a gate condition rather than a courtesy review.

| # | Deliverable / Activity | Zapico (PM / Lead Dev) | Gregorio (SA / QA Lead) | Roquid (QA / Testing) | Client (TravelBean MNL) | Independent Verifier |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | SWOT Analysis & Problem Prioritisation | A / R | C | C | C | Gregorio |
| 2 | Software Requirements Specification (SRS) | A | R | C | C | Roquid |
| 3 | Software Project Plan & Project Charter | A / R | C | C | I / Approver | Gregorio |
| 4 | System Architecture & Network Topology | C | A / R | C | I | Zapico |
| 5 | ADR-001 Architecture Ratification | A / R | C | I | I / Approver | Gregorio |
| 6 | Nine-Table Database DDL & ERD | A / R | C | I | I | Gregorio |
| 7 | API Session & RBAC Engine (server-side) | A / R | C | C | I | Gregorio |
| 8 | React 19 SPA Client Architecture | A / R | C | I | I | Roquid |
| 9 | Figma Touch UI Wireframes (7 screens) | C | A / R | C | C / Approver | Roquid |
| 10 | Master Data CRUD (Product / Ingredient / Event / Recipe) | A | R | C | I | Zapico |
| 11 | Client Master Data Load (menu, recipes, costs, events) | C | C | A / R | C / Provider | Gregorio |
| 12 | Touch POS Interface & Cart Engine | A / R | C | C | I | Roquid |
| 13 | Atomic Recipe Deduction Engine & Ledger | A / R | C | C | I | Gregorio |
| 14 | Low-Stock Alerting Module | C | A | R | I | Gregorio |
| 15 | IndexedDB Queue & UUIDv4 Idempotency Engine | A / R | C | C | I | Roquid |
| 16 | USB Recovery Package & CSV Ingestion Engine | A / R | C | C | I | Roquid |
| 17 | PhpSpreadsheet Four-Tab Export Engine | C | A | R | I | Gregorio |
| 18 | Automated Daily .sql Backup & USB Mirror | A / R | C | I | I | Gregorio |
| 19 | Test Plan Authoring (T01–T14) | C | A / R | C | I | Zapico |
| 20 | Test Execution & Defect Logging | I | A | R | C | Gregorio |
| 21 | User Operational Manual & Installation Guide | C | A / R | C | I / Approver | Roquid |
| 22 | Barista & Owner Training Delivery | C | C | A / R | C / Sign-off | Client |
| 23 | Production Deployment & Hotspot Configuration | A / R | C | C | I | Roquid |
| 24 | User Acceptance Testing & Sign-Off | A | R | R | A / Sign-off | Client & Faculty Evaluator |
| 25 | Final Thesis Manuscript & Defence | A / R | R | R | I | Faculty Evaluator |

Reading the matrix as a governance control. Rows 14 and 17 are the specific cases the audit found defective in predecessor revisions. In both, the Responsible party (Roquid) is no longer the verifier; Gregorio is Accountable for verification, ensuring that construction and validation are separated. Row 2 and Row 19 similarly separate authorship from verification by placing the verifier with a different member than the author. Row 24 deliberately assigns Accountability jointly to the Project Manager and the Industry Client, because acceptance is a client authority and cannot be self-granted by the development team.

Workload balance check. Against the twenty-five activities above, Zapico holds Responsibility on eleven, Gregorio on ten, and Roquid on nine. This distribution deliberately corrects the audited condition in which the Project Manager was the sole owner of six of ten work phases while the other two members were merely "Informed" on the two highest-risk technical items — the React SPA and the PHP API. No member now exceeds three concurrent critical-path tasks in any single sprint (§5.1).

# SECTION 2 — SYSTEM ARCHITECTURE & TECHNICAL SPECIFICATIONS

## 2.1 Architecture Overview

### 2.1.1 Architectural Ratification

VenueVue utilises a modified Three-Tier Client-Server Architecture deployed strictly within a local, self-contained, internet-independent environment. This architecture is ratified by ADR-001 (Appendix I, §7.1), which is incorporated into this Project Plan by reference and carries binding force.

The ratification record is explicit on three points of historical technology change, each of which resolves a divergence identified during the audit:

1. The React 19 Single Page Application is the ratified client tier. It replaces, and renders superseded, all native mobile client specifications.

2. The Flutter / SQLite client architecture is formally retired. Both Flutter prototype codebases that existed at the time of audit are frozen and moved to the archive/flutter-prototype branch. They are retained solely as interface design references and receive no further development, no feature work, and no defect remediation. They are not part of the delivered system and must not be presented as such.

3. Hosted cloud services are excluded. The React prototype implementation carried a dependency on Supabase (hosted PostgreSQL with GoTrue authentication, accessed over the public internet). This dependency is removed during Sprint 4 and replaced by the local PHP API defined in Section 4. The word "Supabase" appears in no approved VenueVue specification, and no hosted database, managed authentication provider, content delivery network, or third-party cloud service may be introduced into any build.

### 2.1.2 Three-Tier Decomposition

| Tier | Operational Component & Host Device | Core Technical Logic and Protocols |
| --- | --- | --- |
| Presentation Tier (Client) | Barista Tablets and Mobile Admin Tablet (Android 8.0+ or iPadOS 14+), executing a React 19 Single Page Application in Google Chrome or Apple Safari | Renders the touch-optimised POS interface, category tab filtering, and administrative console. Manages cart state, client-side input validation, cash change computation, and the IndexedDB transaction queue during network partitions. Executes as a Progressive Web App or Kiosk WebView container where supported. |
| Communication Layer | Local Wi-Fi Wireless Hotspot on the 192.168.137.x subnet | Carries HTTP REST request/response cycles and JSON transaction payloads directly between tablets and the host laptop. Requires no external router, no switching hardware, and no internet bandwidth. |
| Application Tier (Business Logic) | Host Laptop Workstation (192.168.137.1) running the Local XAMPP Server Environment | Serves the compiled React static assets; executes PHP 8.x backend logic; validates session tokens and enforces API-level role-based access control; resolves product prices authoritatively; executes atomic recipe deduction algorithms under row-level locking; enforces UUIDv4 idempotency; manages offline data ingestion; writes the inventory movement ledger and security audit log; compiles four-tab Excel exports via PhpSpreadsheet. |
| Data Tier (Persistence) | Host Laptop Workstation — MySQL 8.x Relational Database Engine (InnoDB) | Stores all core business entities across nine relational tables using PDO prepared statements, foreign key constraints, and ACID transactions. Guarantees relational integrity, inventory movement traceability, and security auditability. Acts as the single authoritative system of record. |

### 2.1.3 Ratified Technology Stack

| System Layer | Selected Technology | Version | Technical Rationale for Selection |
| --- | --- | --- | --- |
| Front-End Framework | React | v19.x | Declarative client-side UI rendering delivering the touch responsiveness required by NFR-02. |
| Routing Engine | TanStack Router / TanStack Start | v1.x | Type-safe client-side routing and state navigation for an offline single-page application. |
| Build System | Vite | v8.x | Fast asset bundling producing static web files directly hostable by Apache, enabling single-source updates across all tablets. |
| CSS Framework | Tailwind CSS | v4.x | Utility-first styling supporting oversized touch targets and centralised design tokens. |
| Client Persistence | IndexedDB | Browser-native | Durable client-side transaction queue. Selected specifically because IndexedDB requires no secure context, unlike service workers, and therefore functions correctly over the plain-HTTP LAN address 192.168.137.x. |
| Back-End Engine | PHP | v8.x | Native server-side script execution within the XAMPP environment; broad offline local-hosting compatibility. |
| Database Engine | MySQL (InnoDB) | v8.x | Relational engine supporting foreign key constraints, SELECT … FOR UPDATE row-level locking, and ACID-compliant transactions required by NFR-05. |
| Local Server Host | XAMPP Stack | v8.2+ | Free, cross-platform local Apache server bundle featuring offline MySQL execution. |
| Excel Generator | PhpSpreadsheet | v1.28+ | Open-source PHP library capable of generating styled, multi-tab .xlsx workbooks entirely offline. |
| Design and Wireframing | Figma | Desktop | Rapid visual prototyping of touch-friendly tablet screen layouts. |
| Version Control | Git / GitHub | v2.x | Distributed source code repository management and team collaboration. |

Note on data-tier selection. The plan does not employ SQLite on client tablets. IndexedDB serves only as a transient transaction queue, never as a system of record. This is a deliberate architectural decision: per-tablet SQLite databases would create N divergent data stores requiring exactly the manual reconciliation that VenueVue exists to eliminate, and would place inventory truth on a device that can be lost, stolen, or left un-synchronised. The host MySQL database is the single authoritative store. Consequently, throughout this document and all VenueVue artefacts, the term "offline" denotes the absence of WAN/Internet connectivity, not autonomous operation of individual tablets.

### 2.1.4 External Interfaces

VenueVue interfaces with hardware devices, peripheral storage media, and data formats without relying on any external cloud application programming interface.

| Interface | Description |
| --- | --- |
| Tablet POS Touch Interface | Responsive React 19 SPA rendered inside standard browsers on 7-inch to 10-inch tablets. Requires no installation. |
| Mobile Admin Console | Administrative interface on an owner-role tablet providing remote file management, stock updates, event administration, and four-tab Excel export triggering. |
| Laptop Administrative Suite | Full-screen host controls for menu configuration, ingredient restocking, recipe mapping, event setup, and financial reporting. |
| Local Wi-Fi Network Interface | Windows Mobile Hotspot broadcast by the host laptop, operating a star topology on 192.168.137.x with the host statically at 192.168.137.1 and tablets receiving leases in the 192.168.137.100+ range. |
| USB Storage Interface | External USB flash drives used for post-event .sql database backup and for manual recovery-package and order-file transfer. |
| Excel File Generator | PhpSpreadsheet compiling database query results into styled four-tab .xlsx workbooks. |

Deliberate exclusions. Physical receipt printing is excluded because TravelBean MNL event customers do not request printed receipts. Online cloud synchronisation is excluded to eliminate internet dependency during live operations and is reinforced by ADR-001. Hardware barcode scanning is excluded because coffee menu items are selected directly through a touchscreen grid. Customer loyalty programmes, integrated e-wallet payment processing, and simultaneous multi-venue site management are excluded because the client operates exclusively on a cash-only, single-event basis.

## 2.2 Operational Availability & Cloud Exclusion (ADR-001)

### 2.2.1 Operational Availability Definition

VenueVue provides operational availability independent of WAN/Internet access, provided that the local host server and the local wireless network remain active.

"Offline" in this study refers specifically to the absence of WAN/Internet connectivity, not to autonomous operation of individual tablets. The host laptop running Apache, PHP 8.x, and MySQL 8.x is the single authoritative store; client tablets are presentation and queueing devices. No hosted or cloud service participates in transaction processing.

### 2.2.2 Single Operational Dependency and Failure-State Definition

The system relies on the local edge host laptop. The behaviour of the system under each distinct failure condition is explicitly defined so that no failure mode is left to improvisation during a live event.

| Failure Condition | System State | Behaviour |
| --- | --- | --- |
| WAN / Internet loss | Wi-Fi LAN and host server remain active. | System remains 100% operational. Tablets submit transactions directly to the local server over the LAN. No user-visible degradation occurs; this is the normal operating condition at event venues. |
| Local host server failure | Server-side transaction processing becomes unavailable. | Client tablets transition to queueing transactions locally in IndexedDB under a PENDING_LOCAL state until server recovery, or until a USB physical recovery package is exported. No captured order is lost, provided the tablet remains powered. |
| Local wireless network loss | Tablets lose LAN connectivity to the host. | Identical to host-server failure from the client's perspective: transactions queue in IndexedDB as PENDING_LOCAL and reconcile automatically when connectivity is restored. |
| Tablet failure or loss | Host retains all committed data. | Committed orders are unaffected. Uncommitted queue contents on the failed device are recoverable only if a USB recovery package was previously exported. Remediation: the operator may export a recovery package at any time, and the plan mandates mid-event export at defined intervals. |
| Database corruption | Host database unusable. | Restore from the most recent automated daily .sql dump (NFR-04). Maximum data loss is bounded at 24 hours. |
| USB drive loss or damage | Host database remains authoritative. | No critical impact. Excel exports and USB backups exist for record-keeping and disaster recovery only; the primary store is unaffected. |

### 2.2.3 Recovery Procedures

| Scenario | Recovery Procedure | Responsible |
| --- | --- | --- |
| Host laptop fails during an event | Staff switch to the temporary paper log. Upon host restoration, missed orders are re-entered into the POS before the next export. | Owner / Operations Manager |
| Tablet failure during an event | No data loss occurs for committed orders; the tablet is only a client. Staff switch to the host laptop directly or to a backup tablet. Any locally queued orders are recovered from the IndexedDB export package if one was taken. | Barista / Owner |
| Database corruption | Restore from the most recent .sql backup file. Maximum data loss is 24 hours. | Owner / Operations Manager |
| Hotspot or LAN failure | Attempt reconnect. Client transactions continue to queue in IndexedDB with no data loss. On restoration, queued transactions reconcile automatically under UUIDv4 idempotency, guaranteeing no duplicates. | Barista |
| Recovery-package ingestion after host loss | Export the IndexedDB PENDING_LOCAL records as a structured JSON recovery package to USB; import on the restored host through the administrative ingestion module, which verifies each client_transaction_id before committing. | Owner / Operations Manager |

### 2.2.4 Binding Cloud Exclusion

No hosted database, managed authentication provider, content delivery network, or third-party cloud service shall be introduced into any build of VenueVue.

The rationale is architectural and contractual, not merely preferential:

1. It falsifies the project's central premise. Section 1.2.1 establishes that cloud-dependent POS systems are unusable at TravelBean MNL's venues. A cloud data tier would reproduce precisely the failure the system was commissioned to eliminate.

2. It breaches the Letter of Agreement. Section 1.1 of the Agreement specifies "a standalone local server environment (PHP/MySQL) running on a primary laptop workstation that creates a local Wi-Fi hotspot for mobile tablet endpoints." A hosted backend does not satisfy that specification.

3. It cannot be demonstrated. The system must be operable and demonstrable at an off-grid event venue. A cloud dependency makes the academic and client demonstration contingent on connectivity that the venue may not provide.

4. It introduces undisclosed data-processing risk. Client operational and financial data would leave the client's premises and be processed by a third party, engaging Data Privacy Act (R.A. 10173) obligations that the Agreement does not contemplate and for which no Data Sharing Agreement exists.

Compliance verification. This exclusion is verified at every phase gate. The verification procedure is: execute a complete sales cycle on the host and client devices while monitoring outbound WAN traffic; the gate passes only on observing zero outbound WAN calls during the cycle. Compliance is additionally evidenced by the absence of any cloud SDK in the build manifest and by an explicit deployment-environment review at gate G10.

## 2.3 Three Data Ingestion Mechanisms

VenueVue replaces the ambiguous and historically contradictory notion of "synchronization protocols" with three precisely defined data-ingestion mechanisms that all terminate at the authoritative host database. The terminology used here is normative and matches the standardised terminology dictionary applied throughout VenueVue documentation.

### 2.3.1 Mechanism 1 — Real-Time Wi-Fi HTTP POST (Primary)

Definition. While the local hotspot is active, a completed order is transmitted immediately over the local area network on the 192.168.137.x subnet to the PHP API and committed to MySQL.

Characteristics.

•  Transport: HTTP POST over the local wireless LAN, carrying a JSON payload conforming to the contract defined in §4.1.

•  Authentication: Bearer session token in the Authorization header, validated server-side on every request.

•  Idempotency: A UUIDv4 client_transaction_id generated on the client before first transmission and protected by a database UNIQUE constraint.

•  Latency target: Mean L_trans ≤ 250 ms and 95th percentile ≤ 500 ms on the local LAN.

•  WAN consumption: None. This is a local-area exchange.

Architectural note on offline-first consistency. This mechanism operates during active sales, which supersedes the earlier post-event-only reconciliation model. Requiring devices to remain silent during active sales creates an unnecessary reconciliation backlog, defers the detection of stock insufficiency until the event is already over, and has no technical justification: a LAN exchange consumes no WAN bandwidth and is therefore fully consistent with the offline-first requirement. The May 2026 Project Technical Documentation's post-event-only model is formally withdrawn.

Client-side durability note. Client durability during partition does not depend on the service worker. IndexedDB is the queue of record and requires no secure context. Because the application is served over the plain-HTTP LAN address http://192.168.137.x, which is not a secure origin, service-worker-based Progressive Web App caching is treated strictly as a progressive enhancement and not as a load-bearing offline mechanism. This distinction is verified on physical tablets at gate G4.

### 2.3.2 Mechanism 2 — IndexedDB Queue and USB Recovery Package (Fail-Safe)

Definition. When Mechanism 1 is unavailable — because the hotspot is down, the host is unavailable, or the LAN is congested — the completed order is durably queued on the client device in IndexedDB under a PENDING_LOCAL state. Queued records may subsequently be exported as a structured JSON recovery package and transferred to the host laptop via USB for idempotent ingestion.

Characteristics.

•  Storage: Browser-native IndexedDB on the client tablet. Selected over service-worker cache and over per-tablet SQLite because it requires no secure context and is not a divergent system of record.

•  State model: See §2.3.4.

•  Recovery export: A structured JSON package containing the full quorum of queued transactions, each retaining its original client_transaction_id, tablet_id, event_id, and line items.

•  Ingestion on the host: The administrative ingestion module validates each record's UUID against the orders table. Records already committed are skipped without re-executing inventory deduction. Records not yet committed are committed atomically.

•  Quota management: The client monitors IndexedDB quota utilisation and raises a visible warning at a configured threshold, prompting the operator to export and clear a recovery package mid-event.

•  Data-loss boundary: No captured order is lost while the tablet remains powered and its browser storage intact. Storage exhaustion is the principal residual risk and is explicitly managed by quota monitoring.

### 2.3.3 Mechanism 3 — Manual Excel/CSV Batch Ingestion (Administrative Fallback)

Definition. Sales spreadsheets exported from a client device are uploaded through the Mobile Admin Console or Laptop Administrative Suite, parsed using the PhpSpreadsheet library, verified against idempotency keys, and committed atomically.

Characteristics.

•  Parser: PhpSpreadsheet v1.28+, reading .xlsx and .csv.

•  Atomicity: Batch ingestion executes within a single MySQL transaction. Any parsing or validation error triggers a complete ROLLBACK, leaving the database in its prior state. Partial ingestion cannot occur.

•  Idempotency: Each row is verified against client_transaction_id before commit; already-committed rows are skipped.

•  Governance classification: This is the administrative fallback of last resort. It is the only one of the three mechanisms that is a candidate for de-scoping under schedule pressure, because it is the least-used in practice and because Objectives 1, 2, 3, 4, and 7 are all satisfiable through Mechanisms 1 and 2 alone. The de-scoping trigger is defined in §5.2.

### 2.3.4 Transaction State Machine

Every tablet-generated order passes through an explicit, auditable state machine. The state machine is the normative specification of client-side durability.

┌──────────────────────┐

│    CREATE ORDER      │

│  (client, offline)   │

└──────────┬───────────┘

│  generate UUIDv4

│  client_transaction_id

▼

┌──────────────────────┐

│    PENDING_LOCAL     │◄──────────────┐

│  (IndexedDB cache)   │               │

└──────────┬───────────┘               │

│                           │

Mechanism 1: HTTP POST attempt         │

│                           │

┌─────────────┴─────────────┐             │

│                           │             │

HTTP 201 / 200              Failure /            │

(created / idempotent        timeout         retry (bounded

replay)                        │           exponential

│                          │            backoff, or

▼                          ▼            USB export)

┌──────────────────┐      ┌──────────────────┐        │

│    COMMITTED     │      │  PENDING_LOCAL   │────────┘

│ (server ack'd)   │      │  (retained)      │

└──────────────────┘      └──────────────────┘

State transitions.

| Transition | Trigger | Server Behaviour | Client Behaviour |
| --- | --- | --- | --- |
| CREATE ORDER → PENDING_LOCAL | Order captured at checkout. | None. | Persist to IndexedDB with a full UUIDv4 client_transaction_id and PENDING_LOCAL status. |
| PENDING_LOCAL → COMMITTED | HTTP 201 Created returned. | Transaction is new; deduct inventory atomically and write ledger and audit rows. | Mark the local record COMMITTED and remove it from the pending set. |
| PENDING_LOCAL → COMMITTED | HTTP 200 OK with "duplicate": true. | client_transaction_id already exists; return the existing result without re-executing deduction. | Mark the local record COMMITTED. Idempotent replay is treated as success. |
| PENDING_LOCAL → PENDING_LOCAL | Network failure, timeout, or any non-2xx response. | No state change; if a business rule rejected the transaction (HTTP 409 or 422), no partial write occurred. | Retain the record. Retry with bounded exponential backoff (maximum three attempts per drain cycle). |
| PENDING_LOCAL → USB package | Operator-initiated export. | None. | Serialise pending records, retaining all identifiers, to a JSON recovery package on removable storage. |

Idempotency guarantee. The database enforces a UNIQUE index constraint on orders.client_transaction_id. Upon receiving any request, the API first checks whether that identifier already exists. If it does, the server returns the existing transaction result without re-executing inventory deductions. If it does not, the server executes the atomic transaction and returns 201 Created. The client promotes a record to COMMITTED only after receiving a successful response. This construction makes duplicate order creation structurally impossible even when a response is lost after the server has already committed, which is the most common real-world duplication path.

# SECTION 3 — DATABASE ARCHITECTURE (9-TABLE CORE SCHEMA)

## 3.1 Data Model Rationale

### 3.1.1 Why the Schema Changed From Six and Eight Tables to Nine

Revision 2.3 expands the core schema to nine tables. The expansion is not a discretionary enhancement; it is the minimum structural change required to satisfy the client's ranked business requirement and the contractual reporting specification. The justification proceeds from the requirement downward to the schema.

The requirement. Problem Rank 5, as recorded in §1.2.2, states: "Lack of historical event performance data — Management cannot identify best-selling products, peak hours, or high-margin events." Objective 8, added in this revision, requires that Tab 1 of the delivered workbook report event name, date, duration, gross revenue, cost of goods sold, and net profit for 100% of closed events. The approved reporting specification defines Tab 1 as containing *"Event Name, Date, Duration, Total Gross Revenue, Net Profit Estimates" and "Total Order Count, Average Order Value (AOV), Primary Payment Distribution."*

The structural obstacle. Neither the six-table schema of Revision 1.1 nor the eight-table schema frozen in Revision 2.2 contained:

1. Any table representing an event — despite the product being named VenueVue and despite event performance being the client's fifth-ranked problem.

2. Any event_id association on orders — meaning no order could be attributed to an event, and no per-event aggregation was possible.

3. Any cost field on ingredients — meaning cost of goods sold could not be computed and no net-profit figure could exist. Revision 2.2 nevertheless promised "actionable profit analytics" and a Tab 1 containing "Net Profit Estimates."

4. Any payment_method column in the Revision 2.2 orders specification — meaning "Primary Payment Distribution" could not be computed either.

The practical consequence was that the flagship client-facing deliverable — the four-tab workbook that replaces two to three hours of manual tallying — could not be produced at all. Four of the four Excel tabs would have been partly or wholly unbuildable: Tab 1 lacked events, profit, and payment distribution.

### 3.1.2 Table-by-Table Justification for Each Addition

| Addition | Table / Column | Business Justification | Requirement Traced |
| --- | --- | --- | --- |
| New table | events | Represents a discrete pop-up engagement with name, venue, date, start/end time, computed duration, and lifecycle status. Without it, no order can be attributed to an event and no per-event or per-venue analysis is possible. Directly resolves Problem Rank 5. | FR-08, Objective 8 |
| New column | orders.event_id (FK → events) | Associates each transaction with the event during which it occurred. This single foreign key is what makes per-event revenue, per-event product mix, and high-margin-event identification possible. | FR-08, Objective 8 |
| New column | ingredients.unit_cost | Records the cost per unit of measure for each raw material. Required to compute cost of goods sold from the recipe quantities already captured in inventory_transactions, and therefore the prerequisite for any net-profit or margin figure. | FR-08, Objective 2, Objective 8 |
| New column | orders.payment_method | Captures tender type. Required to produce the "Primary Payment Distribution" element of Tab 1, and forward-compatible should the client later extend beyond cash. Constrained to cash at present, consistent with the client's cash-only single-event operating model. | FR-08, Objective 8 |
| New column | orders.client_transaction_id (UUIDv4, UNIQUE) | The idempotency key. Without it, no deduplication is possible and every lost response produces a duplicate order and a duplicate inventory deduction. This column is the foundation of the R_duplicate = 0% guarantee. | FR-06, Objective 6 |
| Retained from Rev 2.2 | inventory_transactions | The append-only movement ledger. Records every stock change with direction, quantity, reason, responsible user, and originating order. Enables inventory audit, waste analysis, and Tab 3 reconciliation. Its absence in the six-table schema made inventory deltas unrecoverable. | FR-04, NFR-07 |
| Retained from Rev 2.2 | audit_logs | The append-only security trail. Records authentication outcomes, authorization denials, administrative overrides, and every committed transaction with client IP. Required for cash-handling accountability and for the Data Privacy Act control promised in the Agreement. | FR-01, NFR-03, NFR-07 |
| New infrastructure table | api_sessions | Stores hashed bearer tokens with expiry and originating tablet. Infrastructure, not a business entity. Required to implement API-level RBAC, which the API specification requires but which no predecessor revision provisioned storage for. | FR-01, Objective 7 |

### 3.1.3 Reconciliation of Column Naming

The audit established that every documented column name in Revision 2.2 differed from the implemented schema, and that the implemented schema lacked a category column despite a functional requirement for category filtering. Revision 2.3 resolves this by adopting the Revision 2.2 documented names as normative and correcting the implementation to match, with the following specific reconciliations:

| Revision 2.2 Documented Name | Implemented (Six-Table) Name | Rev 2.3 Resolution |
| --- | --- | --- |
| INGREDIENTS.current_stock | current_quantity | Adopt current_stock (documented name is normative). |
| INGREDIENTS.minimum_stock | safety_stock, reorder_point | Adopt minimum_stock; reorder_point is not required by any requirement and is dropped. |
| INGREDIENTS.updated_at | absent | Adopt updated_at with automatic ON UPDATE. |
| — | cost_per_unit | Replaced by unit_cost, which is the name used in profiling and reporting. |
| PRODUCTS.product_name | name | Adopt product_name. |
| PRODUCTS.unit_price | base_price | Adopt unit_price. |
| PRODUCTS.category | absent | Add `category` — required by FR-02 category tabs. |
| USERS.role ENUM | ENUM('admin','barista') | Adopt ENUM('BARISTA','OWNER') per the documented role vocabulary. |
| RECIPE_ITEMS.recipe_item_id | recipe_id | Adopt recipe_item_id. |
| ORDER_ITEMS.order_item_id | item_id | Adopt order_item_id. |
| ORDERS.tablet_id, committed_at | absent | Add both; tablet_id supports collision diagnosis and per-device reconciliation. |

### 3.1.4 Data Model Summary

The resulting schema comprises nine core business tables and one infrastructure table:

| # | Table | Classification | Purpose |
| --- | --- | --- | --- |
| 1 | users | Core | Account credentials, role assignment, and activation state. |
| 2 | events | Core | Discrete pop-up engagements with venue, schedule, and duration. |
| 3 | products | Core | Menu items with category classification and retail price. |
| 4 | ingredients | Core | Raw materials with unit of measure, stock level, minimum threshold, and unit cost. |
| 5 | recipe_items | Core | Junction table mapping products to required raw material quantities. |
| 6 | orders | Core | Transaction headers with idempotency key, event attribution, and tender data. |
| 7 | order_items | Core | Transaction line items with price snapshots. |
| 8 | inventory_transactions | Core | Append-only stock movement ledger. |
| 9 | audit_logs | Core | Append-only security and administrative audit trail. |
| — | api_sessions | Infrastructure | Bearer session tokens for API-level RBAC. |

## 3.2 Production SQL DDL Script

The following script is the complete, ready-to-execute schema definition for VenueVue Revision 2.3, targeting MySQL 8.x on the InnoDB engine with utf8mb4 collation.

-- =====================================================================

--  VENUEVUE — CORE DATABASE SCHEMA

--  Document Revision 2.3 (Final Architecture-Reconciled Baseline)

--  Date: 2026-09-23

--  Target: MySQL 8.x / InnoDB / utf8mb4 / utf8mb4_unicode_ci

--

--  Composition: 9 core business tables + 1 infrastructure table

--    Core:           users, events, products, ingredients, recipe_items,

--                    orders, order_items, inventory_transactions, audit_logs

--    Infrastructure: api_sessions

--

--  This script supersedes the six-table ddl_core_tables.sql and the

--  eight-table specification frozen in Revision 2.2. It adds the EVENTS

--  entity, ORDERS.event_id, ORDERS.payment_method, INGREDIENTS.unit_cost,

--  and ORDERS.client_transaction_id, without which the contractually

--  specified four-tab Excel report cannot be produced.

-- =====================================================================

SET NAMES utf8mb4;

SET time_zone = '+08:00';          -- Philippine Standard Time

SET FOREIGN_KEY_CHECKS = 1;

CREATE DATABASE IF NOT EXISTS venuevue_db

DEFAULT CHARACTER SET utf8mb4

COLLATE utf8mb4_unicode_ci;

USE venuevue_db;

-- ---------------------------------------------------------------------

-- 1. USERS

--    Account credentials and role assignment. Passwords are stored

--    exclusively as password_hash() output; no plaintext credential is

--    ever persisted. Role vocabulary is BARISTA / OWNER per Rev 2.3

--    reconciliation (§3.1.3).

-- ---------------------------------------------------------------------

CREATE TABLE users (

user_id        INT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

username       VARCHAR(50)  NOT NULL UNIQUE,

password_hash  VARCHAR(255) NOT NULL,

role           ENUM('BARISTA','OWNER') NOT NULL DEFAULT 'BARISTA',

is_active      TINYINT(1)   NOT NULL DEFAULT 1,

created_at     TIMESTAMP    NOT NULL DEFAULT CURRENT_TIMESTAMP,

INDEX idx_users_role (role),

INDEX idx_users_active (is_active)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 2. EVENTS  (NEW in Rev 2.3)

--    A discrete pop-up engagement. This table is the structural

--    prerequisite for per-event revenue, per-event product mix, and

--    high-margin-event identification — i.e. for resolving the client's

--    Priority Rank 5 problem and for producing Tab 1 of the workbook

--    ("Event Name, Date, Duration").

-- ---------------------------------------------------------------------

CREATE TABLE events (

event_id       INT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

event_name     VARCHAR(150)  NOT NULL,

venue          VARCHAR(150)  NULL,

event_date     DATE          NOT NULL,

start_time     TIME          NULL,

end_time       TIME          NULL,

duration_hours DECIMAL(5,2)  NULL,   -- Tab 1 "Duration"

status         ENUM('PLANNED','ACTIVE','CLOSED') NOT NULL DEFAULT 'PLANNED',

notes          VARCHAR(255)  NULL,

created_at     TIMESTAMP     NOT NULL DEFAULT CURRENT_TIMESTAMP,

INDEX idx_events_date   (event_date),

INDEX idx_events_status (status)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 3. PRODUCTS

--    Menu items. 'category' is required by FR-02 (category tab

--    filtering) and was absent from the implemented six-table schema.

-- ---------------------------------------------------------------------

CREATE TABLE products (

product_id   INT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

product_name VARCHAR(100)  NOT NULL UNIQUE,

category     VARCHAR(50)   NOT NULL DEFAULT 'Uncategorised',

unit_price   DECIMAL(10,2) NOT NULL DEFAULT 0.00,

is_active    TINYINT(1)    NOT NULL DEFAULT 1,

created_at   TIMESTAMP     NOT NULL DEFAULT CURRENT_TIMESTAMP,

INDEX idx_products_category (category),

INDEX idx_products_active   (is_active)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 4. INGREDIENTS

--    Raw materials tracked in grams, millilitres, or discrete units.

--    'unit_cost' is NEW in Rev 2.3 and is the prerequisite for cost of

--    goods sold and therefore for the "Net Profit Estimates" element

--    of Tab 1.

-- ---------------------------------------------------------------------

CREATE TABLE ingredients (

ingredient_id   INT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

ingredient_name VARCHAR(100)  NOT NULL UNIQUE,

unit            ENUM('g','mL','units') NOT NULL DEFAULT 'mL',

current_stock   DECIMAL(12,3) NOT NULL DEFAULT 0.000,

minimum_stock   DECIMAL(12,3) NOT NULL DEFAULT 0.000,

unit_cost       DECIMAL(10,4) NOT NULL DEFAULT 0.0000,

is_active       TINYINT(1)    NOT NULL DEFAULT 1,

updated_at      TIMESTAMP     NOT NULL DEFAULT CURRENT_TIMESTAMP

ON UPDATE CURRENT_TIMESTAMP,

CONSTRAINT chk_ingredient_stock_nonneg CHECK (current_stock >= 0),

INDEX idx_ingredients_active (is_active),

INDEX idx_ingredients_stock  (current_stock, minimum_stock)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 5. RECIPE_ITEMS  (junction)

--    Maps a product to the raw material quantities consumed per unit

--    sold. Drives the automatic multi-ingredient deduction engine.

-- ---------------------------------------------------------------------

CREATE TABLE recipe_items (

recipe_item_id    INT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

product_id        INT UNSIGNED NOT NULL,

ingredient_id     INT UNSIGNED NOT NULL,

quantity_required DECIMAL(12,3) NOT NULL DEFAULT 0.000,

created_at        TIMESTAMP     NOT NULL DEFAULT CURRENT_TIMESTAMP,

UNIQUE KEY uq_product_ingredient (product_id, ingredient_id),

CONSTRAINT fk_recipe_product FOREIGN KEY (product_id)

REFERENCES products(product_id)    ON DELETE CASCADE,

CONSTRAINT fk_recipe_ingredient FOREIGN KEY (ingredient_id)

REFERENCES ingredients(ingredient_id) ON DELETE RESTRICT,

CONSTRAINT chk_recipe_qty CHECK (quantity_required > 0),

INDEX idx_recipe_product    (product_id),

INDEX idx_recipe_ingredient (ingredient_id)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 6. ORDERS

--    Transaction headers. client_transaction_id is the UUIDv4

--    idempotency key and carries a UNIQUE constraint that makes

--    duplicate order creation structurally impossible. event_id

--    enables per-event reporting. payment_method supports the

--    "Primary Payment Distribution" element of Tab 1.

--    Note: user_id is always derived server-side from the authenticated

--    session and is never accepted from the client payload.

-- ---------------------------------------------------------------------

CREATE TABLE orders (

order_id              BIGINT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

client_transaction_id CHAR(36)      NOT NULL,

user_id               INT UNSIGNED  NOT NULL,

tablet_id             VARCHAR(16)   NOT NULL,

event_id              INT UNSIGNED  NULL,

payment_method        ENUM('cash')  NOT NULL DEFAULT 'cash',

total_amount          DECIMAL(10,2) NOT NULL DEFAULT 0.00,

cash_tendered         DECIMAL(10,2) NULL,

change_due            DECIMAL(10,2) NULL,

created_at            TIMESTAMP     NOT NULL DEFAULT CURRENT_TIMESTAMP,

committed_at          TIMESTAMP     NULL,

UNIQUE KEY uq_orders_client_txn (client_transaction_id),

CONSTRAINT fk_orders_user  FOREIGN KEY (user_id)

REFERENCES users(user_id)   ON DELETE RESTRICT,

CONSTRAINT fk_orders_event FOREIGN KEY (event_id)

REFERENCES events(event_id) ON DELETE SET NULL,

INDEX idx_orders_event   (event_id),

INDEX idx_orders_created (created_at),

INDEX idx_orders_tablet  (tablet_id),

INDEX idx_orders_user    (user_id)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 7. ORDER_ITEMS

--    Line items. unit_price is a snapshot of the server-resolved price

--    at the moment of sale, so that later menu price changes never

--    rewrite historical revenue.

-- ---------------------------------------------------------------------

CREATE TABLE order_items (

order_item_id BIGINT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

order_id      BIGINT UNSIGNED NOT NULL,

product_id    INT UNSIGNED    NOT NULL,

quantity      INT UNSIGNED    NOT NULL DEFAULT 1,

unit_price    DECIMAL(10,2)   NOT NULL DEFAULT 0.00,

CONSTRAINT fk_items_order FOREIGN KEY (order_id)

REFERENCES orders(order_id)     ON DELETE CASCADE,

CONSTRAINT fk_items_product FOREIGN KEY (product_id)

REFERENCES products(product_id) ON DELETE RESTRICT,

CONSTRAINT chk_order_item_qty_positive CHECK (quantity > 0),

INDEX idx_order_items_order   (order_id),

INDEX idx_order_items_product (product_id)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 8. INVENTORY_TRANSACTIONS  (append-only movement ledger)

--    Every stock change is recorded with direction, magnitude, reason,

--    responsible user, and originating order. Records are never

--    updated or deleted. Supports inventory audit, waste analysis,

--    Tab 3 reconciliation, and the A_deduction metric.

-- ---------------------------------------------------------------------

CREATE TABLE inventory_transactions (

inventory_transaction_id BIGINT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

ingredient_id INT UNSIGNED NOT NULL,

user_id       INT UNSIGNED NOT NULL,

order_id      BIGINT UNSIGNED NULL,     -- NULL for RESTOCK / ADJUSTMENT

transaction_type ENUM('SALE','RESTOCK','ADJUSTMENT') NOT NULL,

quantity_delta   DECIMAL(12,3) NOT NULL, -- negative for SALE

reason        VARCHAR(255) NULL,

created_at    TIMESTAMP NOT NULL DEFAULT CURRENT_TIMESTAMP,

CONSTRAINT fk_invtx_ingredient FOREIGN KEY (ingredient_id)

REFERENCES ingredients(ingredient_id) ON DELETE RESTRICT,

CONSTRAINT fk_invtx_user FOREIGN KEY (user_id)

REFERENCES users(user_id) ON DELETE RESTRICT,

CONSTRAINT fk_invtx_order FOREIGN KEY (order_id)

REFERENCES orders(order_id) ON DELETE SET NULL,

CONSTRAINT chk_invtx_delta_nonzero CHECK (quantity_delta <> 0),

INDEX idx_invtx_ingredient_created (ingredient_id, created_at),

INDEX idx_invtx_type   (transaction_type),

INDEX idx_invtx_order  (order_id),

INDEX idx_invtx_created (created_at)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 9. AUDIT_LOGS  (append-only security and administrative trail)

--    Records authentication outcomes, authorization denials,

--    administrative overrides, and every committed transaction.

--    Required for cash-handling accountability under NFR-07 and for

--    the Data Privacy Act control promised in the Letter of Agreement.

-- ---------------------------------------------------------------------

CREATE TABLE audit_logs (

audit_log_id BIGINT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

user_id      INT UNSIGNED NULL,

action       VARCHAR(64)  NOT NULL,   -- LOGIN_OK, LOGIN_FAIL, RBAC_DENIED,

-- ORDER_COMMIT, STOCK_OVERRIDE, ...

entity_type  VARCHAR(32)  NULL,       -- ORDER | INGREDIENT | PRODUCT | EVENT | USER

entity_id    VARCHAR(64)  NULL,

details      JSON         NULL,

ip_address   VARCHAR(45)  NULL,       -- supports IPv6

created_at   TIMESTAMP    NOT NULL DEFAULT CURRENT_TIMESTAMP,

CONSTRAINT fk_audit_user FOREIGN KEY (user_id)

REFERENCES users(user_id) ON DELETE SET NULL,

INDEX idx_audit_action_created (action, created_at),

INDEX idx_audit_user_created   (user_id, created_at),

INDEX idx_audit_entity         (entity_type, entity_id)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- ---------------------------------------------------------------------

-- 10. API_SESSIONS  (infrastructure — not a business entity)

--     Bearer session tokens for API-level Role-Based Access Control.

--     Only the SHA-256 hash of each token is stored; the raw token is

--     never persisted. Provisioned in Rev 2.3 because the API security

--     specification requires session validation but no predecessor

--     revision provisioned storage for it.

-- ---------------------------------------------------------------------

CREATE TABLE api_sessions (

session_id BIGINT UNSIGNED AUTO_INCREMENT PRIMARY KEY,

user_id    INT UNSIGNED NOT NULL,

token_hash CHAR(64)     NOT NULL UNIQUE,   -- SHA-256 hex digest

tablet_id  VARCHAR(16)  NULL,

issued_at  TIMESTAMP    NOT NULL DEFAULT CURRENT_TIMESTAMP,

expires_at DATETIME     NOT NULL,

CONSTRAINT fk_sessions_user FOREIGN KEY (user_id)

REFERENCES users(user_id) ON DELETE CASCADE,

INDEX idx_sessions_expiry (expires_at),

INDEX idx_sessions_user   (user_id)

) ENGINE=InnoDB DEFAULT CHARSET=utf8mb4 COLLATE=utf8mb4_unicode_ci;

-- =====================================================================

--  LEAST-PRIVILEGE APPLICATION ACCOUNT

--  Replaces the previously shipped MySQL 'root' account with an empty

--  password. The application account is granted no DELETE and no DROP

--  privilege, consistent with the May 2026 Project Technical

--  Documentation §7.5.2 control and with NFR-03.

-- =====================================================================

-- CREATE USER 'venuevue_app'@'localhost' IDENTIFIED BY '<strong-password>';

-- GRANT SELECT, INSERT, UPDATE ON venuevue_db.* TO 'venuevue_app'@'localhost';

-- FLUSH PRIVILEGES;

-- =====================================================================

--  INITIAL SEED DATA

--  Exactly two accounts, matching the two-role model. The placeholder

--  hashes below MUST be replaced with real password_hash() output

--  before deployment. These are not demonstration credentials and must

--  never be committed with a usable password.

-- =====================================================================

INSERT INTO users (username, password_hash, role) VALUES

('owner',   '$2y$10$REPLACE_WITH_REAL_PASSWORD_HASH_A', 'OWNER'),

('barista', '$2y$10$REPLACE_WITH_REAL_PASSWORD_HASH_B', 'BARISTA');

-- =====================================================================

--  POST-MIGRATION VERIFICATION QUERIES

-- =====================================================================

-- Expect exactly 10 tables (9 core + 1 infrastructure):

--   SELECT COUNT(*) AS table_count

--     FROM information_schema.tables

--    WHERE table_schema = 'venuevue_db';

--

-- Expect the EVENTS and cost columns to exist:

--   SHOW COLUMNS FROM orders      LIKE 'client_transaction_id';

--   SHOW COLUMNS FROM orders      LIKE 'event_id';

--   SHOW COLUMNS FROM ingredients LIKE 'unit_cost';

--

-- Expect the idempotency constraint to be enforced:

--   SHOW INDEX FROM orders WHERE Key_name = 'uq_orders_client_txn';

--

-- Expect full referential integrity:

--   SELECT TABLE_NAME, CONSTRAINT_NAME, REFERENCED_TABLE_NAME

--     FROM information_schema.KEY_COLUMN_USAGE

--    WHERE TABLE_SCHEMA = 'venuevue_db'

--      AND REFERENCED_TABLE_NAME IS NOT NULL;

### 3.2.1 Referential Integrity Summary

| Child Table | Foreign Key Column | References | On Delete | Rationale |
| --- | --- | --- | --- | --- |
| recipe_items | product_id | products.product_id | CASCADE | Removing a discontinued product removes its recipe mapping; no orphan recipes. |
| recipe_items | ingredient_id | ingredients.ingredient_id | RESTRICT | An ingredient still used by any recipe cannot be deleted; it must be deactivated instead. Protects historical deduction accuracy. |
| orders | user_id | users.user_id | RESTRICT | Sales attribution is never orphaned. |
| orders | event_id | events.event_id | SET NULL | Deleting an event must not destroy financial records; the order is retained and reclassified as unattributed. |
| order_items | order_id | orders.order_id | CASCADE | Line items have no meaning without their parent order. |
| order_items | product_id | products.product_id | RESTRICT | Price-history integrity; products are deactivated, not deleted. |
| inventory_transactions | ingredient_id | ingredients.ingredient_id | RESTRICT | The movement ledger is append-only and must remain complete. |
| inventory_transactions | user_id | users.user_id | RESTRICT | Every stock movement remains attributable. |
| inventory_transactions | order_id | orders.order_id | SET NULL | Retains the movement record for audit even if the order is removed. |
| audit_logs | user_id | users.user_id | SET NULL | Security history survives account removal. |
| api_sessions | user_id | users.user_id | CASCADE | Deactivating an account terminates its sessions. |

### 3.2.2 Mandatory InnoDB Rationale

The InnoDB engine is not interchangeable with MyISAM for this schema. InnoDB is required because the system depends upon four capabilities that MyISAM does not provide: (1) foreign key constraint enforcement, which underpins the referential integrity summary above; (2) transactional commit and rollback, which is the basis of the atomic order-plus-deduction-plus-ledger write specified in §4.2; (3) row-level locking through SELECT … FOR UPDATE, which is the mechanism that prevents lost updates when two barista tablets submit orders concurrently; and (4) crash recovery, which protects the database against power loss at an event venue. MyISAM provides none of these and additionally performs table-level locking that would serialise all concurrent tablet writes.

# SECTION 4 — API & TRANSACTIONAL SPECIFICATIONS

## 4.1 Order Ingestion Contract & JSON Envelope

### 4.1.1 Contract Status and Freezing

The order ingestion contract defined in this section is frozen. It is reproduced verbatim as an appendix to the Software Requirements Specification and is treated as immutable for the remainder of the project. Neither the client developer nor the backend developer may alter field names, nesting structure, or semantics unilaterally; any change requires a revision to this Project Plan and re-verification of all scenarios in §5.1.

The audit of predecessor revisions established that the client and server contracts were mutually incompatible: the Flutter clients transmitted a flat order map while the PHP backend required a nested {"order": {…}} envelope and rejected all such requests with HTTP 400, and neither client ever transmitted the items array the backend required. The result was a 0% sync success rate despite substantial code existing on both sides. This contract is designed to make that class of defect structurally impossible by specifying the wire format once, in one place, as a normative artefact.

### 4.1.2 Transport and Headers

| Aspect | Specification |
| --- | --- |
| Method | POST |
| Endpoint | http://192.168.137.1/venuevue_api/sync.php |
| Transport | Plain HTTP over the local wireless LAN. No WAN transit occurs. |
| Content-Type | application/json |
| Accept | application/json |
| Authorization | Bearer <session_token> — mandatory. Requests without a valid token receive HTTP 401. |
| CORS Origin | Access-Control-Allow-Origin is restricted to the application origin (http://192.168.137.1). Wildcard * is prohibited. |
| Timeout | Client-side request timeout is 10 seconds. |
| Preflight | OPTIONS returns HTTP 204 with CORS headers. |

Prohibition on wildcard CORS. Revision 2.3 expressly prohibits Access-Control-Allow-Origin: *. The predecessor backend emitted a wildcard origin, which — combined with the absence of authentication — permitted any device that joined the hotspot, including a customer's telephone, to issue arbitrary browser-originated requests against the ingest endpoint.

### 4.1.3 Request Payload Definition

{

"client_transaction_id": "550e8400-e29b-41d4-a716-446655440000",

"tablet_id": "T-01",

"event_id": 7,

"order": {

"cash_tendered": 500.00,

"created_at": "2026-11-14 14:30:15"

},

"items": [

{ "product_id": 12, "quantity": 2 },

{ "product_id": 5,  "quantity": 1 }

]

}

### 4.1.4 Field Dictionary

| Field | Type | Required | Constraint / Semantics |
| --- | --- | --- | --- |
| client_transaction_id | string | Yes | UUIDv4. Must match ^[0-9a-f]{8}-[0-9a-f]{4}-4[0-9a-f]{3}-[89ab][0-9a-f]{3}-[0-9a-f]{12}$ (case-insensitive). Generated on the client before first transmission and never regenerated for the same basket. This is the sole idempotency key. Truncated, sequential, hashed-timestamp, or locally-derived identifiers are prohibited. |
| tablet_id | string | Yes | Device identifier, maximum 16 characters, e.g. T-01. Enables per-device reconciliation and duplicate diagnosis. |
| event_id | integer | No | Foreign key to events.event_id. Omitted when no event is active. Enables per-event reporting (FR-08). |
| order | object | Yes | Transaction header. Must be an object, not a scalar. |
| order.cash_tendered | decimal | No | Amount of cash presented. When supplied, must be greater than or equal to the server-computed total; otherwise HTTP 422 is returned. |
| order.created_at | string | No | Client-side capture timestamp. The server records its own created_at and committed_at authoritatively; the client value is retained for reconciliation and latency measurement only. |
| items | array | Yes | Must contain at least one element. An empty or absent array is rejected with HTTP 422. |
| items[].product_id | integer | Yes | Must be a positive integer referencing an active product. |
| items[].quantity | integer | Yes | Must be a positive integer, greater than zero and not exceeding the configured per-line maximum (100). Negative and zero quantities are rejected explicitly. |
| items[].unit_price | — | Forbidden | Must never be transmitted. Prices are resolved exclusively server-side from products.unit_price, satisfying FR-03's requirement that prices are locked to internal system menu tables. Any client-supplied price is ignored. |
| user_id | — | Forbidden | Must never be transmitted. The server derives the acting user from the validated session token. Transmitting a client-supplied user_id was the defect that caused every predecessor order to be attributed to user ID 1. |

### 4.1.5 Response Codes and Semantics

| HTTP Status | Condition | Body | Client Action |
| --- | --- | --- | --- |
| 201 Created | Transaction is new; committed successfully. | {"success":true,"order_id":…,"duplicate":false,"total_amount":…,"change_due":…,"low_stock":[…],"server_time":"…"} | Mark local record COMMITTED; surface any low-stock badges; record server_time for latency measurement. |
| 200 OK | client_transaction_id already exists. No re-deduction is performed. | {"success":true,"order_id":…,"duplicate":true,"message":"Already committed; no re-deduction performed."} | Mark local record COMMITTED. Idempotent replay is a success condition, not an error. |
| 401 Unauthorized | Session token absent, malformed, expired, or belonging to an inactive account. | {"success":false,"error":"…"} | Abort the drain cycle; force re-authentication. Do not retry blindly. |
| 403 Forbidden | Authenticated, but the role does not permit the requested operation. | {"success":false,"error":"…"} | Abort; log the denial. An audit_logs row is written server-side. |
| 405 Method Not Allowed | Any method other than POST or OPTIONS. | {"success":false,"error":"Method not allowed"} | Programming error; do not retry. |
| 409 Conflict | Insufficient ingredient stock for the requested order. | {"success":false,"error":"Insufficient stock","ingredient_id":…,"required":…,"available":…} | Do not retry unchanged. Surface a stock-insufficiency message to the barista. Inventory remains untouched. |
| 422 Unprocessable Entity | Malformed JSON, missing required field, non-positive quantity, invalid UUID, unknown or inactive product, or cash tendered below total. | {"success":false,"error":"…"} | Programming or data error; do not retry unchanged. Log for defect triage. |
| 500 Internal Server Error | Unhandled server fault. Database state is unchanged (transaction rolled back). | {"success":false,"error":"Transaction failed; database state unchanged"} | Retain PENDING_LOCAL and retry with bounded backoff. Internal exception detail is never returned to the client; it is written to the server error log only. |

### 4.1.6 Idempotency Semantics

The idempotency guarantee rests on three cooperating mechanisms:

1. Client-generated key. A UUIDv4 is minted on the tablet before the first transmission attempt and is never regenerated for the same basket.

2. Database uniqueness constraint. orders.client_transaction_id carries UNIQUE KEY uq_orders_client_txn.

3. Server pre-check. Before any deduction or insert executes, the API queries for an existing order bearing that identifier. If found, the server returns the existing result immediately — without re-executing inventory deduction — and responds HTTP 200 with "duplicate": true.

Why this is sufficient. The most common real-world duplication path is not a user double-click; it is a lost response. The server commits the transaction, then the network drops, the tablet sleeps, or the browser is closed before the response is received. The client therefore retains the record as PENDING_LOCAL and retries. Without idempotency enforcement, that retry creates a second order and a second inventory deduction. With the three mechanisms above, the retry is recognised and absorbed. This is why the plan mandates that the client promote a record to COMMITTED only upon receipt of a successful response, and that a 200 duplicate response be treated as success rather than failure.

### 4.1.7 Worked Example

Scenario. Two baristas on tablets T-01 and T-02 each sell one 16oz Iced Salted Caramel Latte (product 12, ₱170.00) and one Americano (product 5, ₱120.00) during event 7.

Request from T-01:

{

"client_transaction_id": "550e8400-e29b-41d4-a716-446655440000",

"tablet_id": "T-01",

"event_id": 7,

"order": { "cash_tendered": 500.00, "created_at": "2026-11-14 14:30:15" },

"items": [ { "product_id": 12, "quantity": 1 }, { "product_id": 5, "quantity": 1 } ]

}

Server processing. Authentication resolves the session to user 2. The product prices ₱170.00 and ₱120.00 are resolved server-side, yielding a total of ₱290.00. The recipe for product 12 requires 18 g espresso beans, 200 mL full-cream milk, 30 mL caramel syrup, 1 cup, 1 dome lid, 1 straw; the recipe for product 5 requires 18 g espresso beans. Requirements are aggregated per ingredient — espresso beans total 36 g across both lines — and the affected ingredients rows are locked with SELECT … FOR UPDATE. Stock sufficiency is verified. The order header is inserted with user_id from the session, tablet_id T-01, and event_id 7. Line items are inserted with the server-resolved price. Each ingredient is decremented and one inventory_transactions row of type SALE with a negative quantity_delta is written per ingredient. An audit_logs row with action ORDER_COMMIT is written. The transaction commits. A 201 Created response is returned with order_id, change_due of ₱210.00, the current low-stock list, and server_time.

Concurrent submission from T-02. Because T-01's transaction holds row-level locks on the affected ingredient rows, T-02's SELECT … FOR UPDATE blocks until T-01 commits. T-02 then reads the post-commit stock values and proceeds against current data. No lost update occurs.

Lost-response replay. If T-01 never receives the 201 response and retries the identical payload, the server finds 550e8400-… already present, returns 200 OK with "duplicate": true, and performs no second deduction.

## 4.2 Production API Engine (sync.php)

The following is the complete, annotated production implementation of the order ingestion endpoint. It is the authoritative engine for Mechanism 1 and is also invoked by Mechanisms 2 and 3 after their respective ingestion modules normalise their input to the contract in §4.1.

<?php

/**

* =====================================================================

*  VENUEVUE — ORDER INGESTION API ENGINE

*  Document Revision 2.3 | 2026-09-23

*  Target: PHP 8.x / MySQL 8.x (InnoDB) / XAMPP

*

*  RESPONSIBILITIES

*    1. Bearer session-token authentication and API-level RBAC.

*    2. Payload parsing and strict schema validation.

*    3. UUIDv4 idempotency enforcement (exactly-once ingestion).

*    4. Authoritative server-side price resolution.

*    5. Atomic multi-ingredient deduction under SELECT ... FOR UPDATE.

*    6. Append-only inventory movement ledger writes.

*    7. Append-only security audit trail writes.

*    8. Low-stock evaluation for the response payload.

*

*  DEFECTS RESOLVED FROM PREDECESSOR IMPLEMENTATIONS

*    - Envelope mismatch that caused HTTP 400 on 100% of requests.

*    - Absence of the items[] array in every client payload.

*    - Complete absence of authentication and role enforcement.

*    - Absence of any idempotency key or uniqueness constraint check.

*    - Absence of row-level locking, permitting lost updates.

*    - Absence of ledger and audit writes, leaving no traceability.

*    - Acceptance of negative quantities, which INCREASED stock.

*    - Return of HTTP 500 for business rule violations instead of 409.

*    - A dead concurrency guard caused by assigning the boolean result

*      of PDOStatement::execute() and comparing it to integer zero.

*    - Disclosure of database and SQL internals via exception messages.

*    - Wildcard CORS permitting any hotspot client to post orders.

*    - MySQL 'root' account with an empty password hardcoded in source.

* =====================================================================

*/

declare(strict_types=1);

/* ---------------------------------------------------------------------

* CONFIGURATION

* Credentials are read from the environment or a git-ignored config

* include. They are never committed to version control. The database

* account is a least-privilege application account, not 'root'.

* ------------------------------------------------------------------- */

const DB_HOST    = 'localhost';

const DB_NAME    = 'venuevue_db';

const DB_USER    = 'venuevue_app';

const DB_PASS    = '';                 // supplied via environment at deploy time

const APP_ORIGIN = 'http://192.168.137.1';

const PER_LINE_QTY_MAX = 100;          // sanity ceiling for a pop-up coffee line

/* ---------------------------------------------------------------------

* RESPONSE HEADERS

* CORS is restricted to the application origin. A wildcard origin is

* expressly prohibited: combined with the shared hotspot it would allow

* any connected device to drive the ingest endpoint from a browser.

* ------------------------------------------------------------------- */

header('Content-Type: application/json; charset=utf-8');

header('Access-Control-Allow-Origin: ' . APP_ORIGIN);

header('Access-Control-Allow-Methods: POST, OPTIONS');

header('Access-Control-Allow-Headers: Content-Type, Authorization');

header('X-Content-Type-Options: nosniff');

if ($_SERVER['REQUEST_METHOD'] === 'OPTIONS') {

http_response_code(204);

exit;

}

/**

* Emit a JSON error response and terminate.

* Never echoes internal exception detail; detail goes to the error log.

*/

function fail(int $code, string $error, array $extra = []): never

{

http_response_code($code);

echo json_encode(['success' => false, 'error' => $error] + $extra,

JSON_UNESCAPED_UNICODE);

exit;

}

/** Fast-path method rejection. */

if ($_SERVER['REQUEST_METHOD'] !== 'POST') {

fail(405, 'Method not allowed');

}

/* ---------------------------------------------------------------------

* DATABASE CONNECTION

* PDO with emulated prepares disabled guarantees genuine server-side

* prepared statements, which is the project's primary SQL injection

* control (NFR-03). ERRMODE_EXCEPTION ensures failures surface as

* exceptions and are caught by the transaction handler below.

* ------------------------------------------------------------------- */

try {

$pdo = new PDO(

'mysql:host=' . DB_HOST . ';dbname=' . DB_NAME . ';charset=utf8mb4',

DB_USER,

DB_PASS,

[

PDO::ATTR_ERRMODE            => PDO::ERRMODE_EXCEPTION,

PDO::ATTR_EMULATE_PREPARES   => false,

PDO::ATTR_DEFAULT_FETCH_MODE => PDO::FETCH_ASSOC,

PDO::ATTR_STRINGIFY_FETCHES  => false,

]

);

} catch (PDOException $e) {

error_log('[VenueVue][DB] ' . $e->getMessage());

fail(500, 'Service temporarily unavailable');

}

/* =====================================================================

* STEP 1 — AUTHENTICATE

* Every request must present a bearer token. Only the SHA-256 hash of

* the token is stored, so a database disclosure does not yield usable

* session credentials. Expired tokens and deactivated accounts are

* rejected identically.

* =================================================================== */

$authHeader = $_SERVER['HTTP_AUTHORIZATION'] ?? '';

$token      = preg_replace('/^Bearer\s+/i', '', $authHeader);

if ($token === '' || $token === null) {

fail(401, 'Missing session token');

}

$authStmt = $pdo->prepare(

'SELECT u.user_id, u.role, s.tablet_id

FROM api_sessions s

JOIN users u ON u.user_id = s.user_id

WHERE s.token_hash = SHA2(?, 256)

AND s.expires_at > NOW()

AND u.is_active  = 1

LIMIT 1'

);

$authStmt->execute([$token]);

$session = $authStmt->fetch();

if (!$session) {

fail(401, 'Invalid or expired session token');

}

/* The acting user is derived from the session and never from the

* payload. This resolves the predecessor defect in which every order

* was attributed to whichever account happened to hold user_id 1. */

$userId = (int) $session['user_id'];

/* =====================================================================

* STEP 2 — PARSE AND VALIDATE

* Validation is strict and total. Each rejection returns 422 and no

* database write occurs.

* =================================================================== */

$raw   = file_get_contents('php://input');

$input = json_decode($raw, true);

if (!is_array($input)) {

fail(422, 'Malformed JSON body');

}

$txnId    = (string) ($input['client_transaction_id'] ?? '');

$tabletId = trim((string) ($input['tablet_id'] ?? ''));

$eventId  = isset($input['event_id']) ? (int) $input['event_id'] : null;

$order    = $input['order'] ?? null;

$items    = $input['items'] ?? null;

/* UUIDv4 shape check. Lowercase or uppercase are both accepted. */

if (!preg_match(

'/^[0-9a-f]{8}-[0-9a-f]{4}-4[0-9a-f]{3}-[89ab][0-9a-f]{3}-[0-9a-f]{12}$/i',

$txnId)) {

fail(422, 'client_transaction_id must be a UUIDv4');

}

if ($tabletId === '') {

fail(422, 'tablet_id is required');

}

if (!is_array($order)) {

fail(422, 'order object is required');

}

if (!is_array($items) || $items === []) {

fail(422, 'items must contain at least one line');

}

/* =====================================================================

* TRANSACTION BEGINS

* Order header, line items, inventory deduction, movement ledger and

* audit log are committed as one atomic unit. Any failure rolls the

* whole unit back, leaving the database in its prior state.

* =================================================================== */

try {

$pdo->beginTransaction();

/* -----------------------------------------------------------------

* STEP 3 — IDEMPOTENCY CHECK

* Executed before any write. A replay returns the existing result

* without re-executing inventory deduction, which is what makes

* R_duplicate = 0% achievable even when a response is lost.

* --------------------------------------------------------------- */

$dupStmt = $pdo->prepare(

'SELECT order_id, total_amount FROM orders

WHERE client_transaction_id = ? LIMIT 1'

);

$dupStmt->execute([$txnId]);

if ($existing = $dupStmt->fetch()) {

$pdo->commit();

http_response_code(200);

echo json_encode([

'success'   => true,

'order_id'  => (int) $existing['order_id'],

'duplicate' => true,

'message'   => 'Transaction already committed; no re-deduction performed.',

], JSON_UNESCAPED_UNICODE);

exit;

}

/* -----------------------------------------------------------------

* STEP 4 — SERVER-SIDE PRICE RESOLUTION AND LINE VALIDATION

* The client never supplies a price. Quantities are validated with

* FILTER_VALIDATE_INT, which rejects negatives, zero, and

* non-numeric input. The predecessor implementation used empty(),

* under which a negative quantity is truthy and therefore passed,

* producing a negative deduction that increased recorded stock.

* --------------------------------------------------------------- */

$total    = 0.0;

$resolved = [];

$priceStmt = $pdo->prepare(

'SELECT unit_price FROM products

WHERE product_id = ? AND is_active = 1 LIMIT 1'

);

foreach ($items as $line) {

if (!is_array($line)) {

fail(422, 'Each item must be an object');

}

$pid = filter_var($line['product_id'] ?? null, FILTER_VALIDATE_INT);

$qty = filter_var($line['quantity']   ?? null, FILTER_VALIDATE_INT);

if ($pid === false || $pid <= 0) {

fail(422, 'product_id must be a positive integer');

}

if ($qty === false || $qty <= 0) {

fail(422, 'quantity must be a positive integer');

}

if ($qty > PER_LINE_QTY_MAX) {

fail(422, 'quantity exceeds the permitted per-line maximum');

}

$priceStmt->execute([$pid]);

$product = $priceStmt->fetch();

if (!$product) {

fail(422, 'Product ' . $pid . ' not found or inactive');

}

$unitPrice  = (float) $product['unit_price'];

$total     += $unitPrice * $qty;

$resolved[] = [

'product_id' => $pid,

'quantity'   => $qty,

'unit_price' => $unitPrice,

];

}

/* Cash sufficiency check. array_key_exists is used rather than

* isset/empty so that a legitimate zero tender is not misread as

* absence. */

$cash = array_key_exists('cash_tendered', $order)

? (float) $order['cash_tendered']

: null;

if ($cash !== null && $cash < $total) {

fail(422, 'cash_tendered is less than the order total');

}

/* -----------------------------------------------------------------

* STEP 5 — REQUIREMENT AGGREGATION AND ROW LOCKING

* Ingredient requirements are aggregated across all lines so that

* a shared ingredient is locked and deducted once. SELECT ... FOR

* UPDATE acquires exclusive row locks, serialising concurrent

* orders from multiple tablets and preventing lost updates. This is

* the mechanism that satisfies NFR-05 and scenarios T02 and T03.

* --------------------------------------------------------------- */

$need = [];

$recipeStmt = $pdo->prepare(

'SELECT ingredient_id, quantity_required

FROM recipe_items

WHERE product_id = ?'

);

foreach ($resolved as $line) {

$recipeStmt->execute([$line['product_id']]);

foreach ($recipeStmt->fetchAll() as $r) {

$iid = (int) $r['ingredient_id'];

$need[$iid] = ($need[$iid] ?? 0.0)

+ ((float) $r['quantity_required'] * $line['quantity']);

}

}

if ($need !== []) {

$ids        = array_keys($need);

$placeholds = implode(',', array_fill(0, count($ids), '?'));

$lockStmt = $pdo->prepare(

"SELECT ingredient_id, current_stock

FROM ingredients

WHERE ingredient_id IN ($placeholds)

FOR UPDATE"

);

$lockStmt->execute($ids);

$stock = [];

foreach ($lockStmt->fetchAll() as $row) {

$stock[(int) $row['ingredient_id']] = (float) $row['current_stock'];

}

foreach ($need as $iid => $qtyNeeded) {

if (($stock[$iid] ?? 0.0) < $qtyNeeded) {

$pdo->rollBack();

http_response_code(409);          // business conflict, not a server fault

echo json_encode([

'success'       => false,

'error'         => 'Insufficient stock',

'ingredient_id' => $iid,

'required'      => $qtyNeeded,

'available'     => $stock[$iid] ?? 0.0,

], JSON_UNESCAPED_UNICODE);

exit;

}

}

}

/* -----------------------------------------------------------------

* STEP 6 — PERSIST ORDER HEADER AND LINE ITEMS

* user_id comes from the session. tablet_id and event_id come from

* the validated payload. unit_price is the server-resolved price

* snapshotted at the moment of sale.

* --------------------------------------------------------------- */

$changeDue = $cash !== null ? ($cash - $total) : null;

$orderStmt = $pdo->prepare(

'INSERT INTO orders

(client_transaction_id, user_id, tablet_id, event_id,

payment_method, total_amount, cash_tendered, change_due, committed_at)

VALUES (?, ?, ?, ?, "cash", ?, ?, ?, NOW())'

);

$orderStmt->execute([

$txnId, $userId, $tabletId, $eventId, $total, $cash, $changeDue,

]);

$orderId = (int) $pdo->lastInsertId();

$itemStmt = $pdo->prepare(

'INSERT INTO order_items (order_id, product_id, quantity, unit_price)

VALUES (?, ?, ?, ?)'

);

foreach ($resolved as $line) {

$itemStmt->execute([

$orderId, $line['product_id'], $line['quantity'], $line['unit_price'],

]);

}

/* -----------------------------------------------------------------

* STEP 7 — APPLY DEDUCTION AND WRITE THE MOVEMENT LEDGER

* rowCount() is used, NOT the return value of execute(), which is a

* boolean. The predecessor guard compared a boolean to integer zero

* and could therefore never fire, rendering lost-update detection

* inert. Each successful deduction additionally writes one

* append-only ledger row, giving full inventory traceability.

* --------------------------------------------------------------- */

$updateStmt = $pdo->prepare(

'UPDATE ingredients

SET current_stock = current_stock - ?

WHERE ingredient_id = ?

AND current_stock >= ?'

);

$ledgerStmt = $pdo->prepare(

'INSERT INTO inventory_transactions

(ingredient_id, user_id, order_id, transaction_type, quantity_delta, reason)

VALUES (?, ?, ?, "SALE", ?, ?)'

);

foreach ($need as $iid => $qtyNeeded) {

$updateStmt->execute([$qtyNeeded, $iid, $qtyNeeded]);

if ($updateStmt->rowCount() !== 1) {

throw new RuntimeException(

'Concurrency conflict on ingredient ' . $iid

);

}

$ledgerStmt->execute([

$iid,

$userId,

$orderId,

-$qtyNeeded,

'Order #' . $orderId,

]);

}

/* -----------------------------------------------------------------

* STEP 8 — SECURITY AUDIT TRAIL

* Every committed transaction is recorded with acting user, entity

* reference, structured detail, and client address. Required by

* NFR-07 and by the Letter of Agreement's Data Privacy control.

* --------------------------------------------------------------- */

$auditStmt = $pdo->prepare(

'INSERT INTO audit_logs

(user_id, action, entity_type, entity_id, details, ip_address)

VALUES (?, ?, ?, ?, ?, ?)'

);

$auditStmt->execute([

$userId,

'ORDER_COMMIT',

'ORDER',

(string) $orderId,

json_encode([

'tablet_id' => $tabletId,

'event_id'  => $eventId,

'total'     => $total,

'lines'     => count($resolved),

], JSON_UNESCAPED_UNICODE),

$_SERVER['REMOTE_ADDR'] ?? null,

]);

$pdo->commit();

/* -----------------------------------------------------------------

* STEP 9 — LOW-STOCK EVALUATION FOR THE RESPONSE

* Evaluated after commit so the badges reflect post-sale reality.

* --------------------------------------------------------------- */

$lowStmt = $pdo->query(

'SELECT ingredient_id, ingredient_name, current_stock, minimum_stock,

unit

FROM ingredients

WHERE is_active = 1

AND current_stock <= minimum_stock

ORDER BY (current_stock - minimum_stock) ASC'

);

$lowStock = $lowStmt->fetchAll();

http_response_code(201);

echo json_encode([

'success'      => true,

'order_id'     => $orderId,

'duplicate'    => false,

'total_amount' => round($total, 2),

'change_due'   => $changeDue !== null ? round($changeDue, 2) : null,

'low_stock'    => $lowStock,

'server_time'  => date('c'),   // enables L_trans measurement on the client

], JSON_UNESCAPED_UNICODE);

} catch (Throwable $e) {

/* Any failure within the transaction rolls back the entire unit.

* Internal detail is logged, never returned. */

if ($pdo->inTransaction()) {

$pdo->rollBack();

}

error_log('[VenueVue][TXN] ' . $e->getMessage()

. ' | txn=' . ($txnId ?? 'n/a')

. ' | tablet=' . ($tabletId ?? 'n/a'));

fail(500, 'Transaction failed; database state unchanged');

}

### 4.2.1 Companion Endpoints Required by the Contract

The ingest engine is the primary endpoint, but three supporting endpoints are required for the system to function as specified. All are subject to the same authentication, CORS, and error-handling standards as sync.php.

| Endpoint | Method | Purpose | Notes |
| --- | --- | --- | --- |
| health.php | GET | Liveness probe used by the client reachability check. Returns {"status":"ok"} with HTTP 200. | Required because the predecessor client probed with HEAD, which the API answered with HTTP 405, causing the reachability check to report the server as permanently offline. |
| auth.php | POST | Validates credentials against users.password_hash using password_verify(), issues a bearer token, and inserts its SHA-256 hash into api_sessions with an expiry. Writes a LOGIN_OK or LOGIN_FAIL audit row. | Foundation of FR-01 and Objective 7. |
| export.php | GET | Invokes the PhpSpreadsheet four-tab workbook generation and streams the .xlsx to the requester. Restricted to the OWNER role; returns HTTP 403 for BARISTA. | Implements FR-07, FR-08, and Objective 5. |

### 4.2.2 Report Generation Specification

export.php produces a four-tab workbook in conformance with the approved reporting specification. Tab 1 is only realisable because of the Rev 2.3 schema additions.

| Tab | Contents | Schema Dependencies |
| --- | --- | --- |
| Tab 1 — Summary | Event Name, Event Date, Duration (hours), Total Gross Revenue, Cost of Goods Sold, Net Profit Estimates, Total Order Count, Average Order Value (AOV), Primary Payment Distribution | events (name, date, duration), orders.event_id, orders.payment_method, ingredients.unit_cost joined through inventory_transactions |
| Tab 2 — Sales by Product | Product Category, Product Name, Volume Sold, Unit Retail Price, Total Revenue per Item | products.category, products.product_name, products.unit_price, order_items |
| Tab 3 — Ingredient Usage | Raw Material Depletion in grams / millilitres / units; Initial Stock vs. Depleted Quantity vs. Remaining Ending Inventory Balance | inventory_transactions (type SALE, quantity_delta), ingredients.current_stock, ingredients.unit |
| Tab 4 — Restock List | Automated procurement recommendations; items that breached configured minimum thresholds, with shortfall quantity and estimated reorder cost | ingredients.minimum_stock, ingredients.current_stock, ingredients.unit_cost |

Cost of goods sold derivation. For each closed event, cost of goods sold is computed as the sum over all inventory_transactions rows of type SALE, restricted to orders belonging to that event, of the absolute quantity depleted multiplied by the ingredient's unit_cost. Net profit is gross revenue less cost of goods sold. This computation is precisely why unit_cost was added to ingredients in Revision 2.3 and why no predecessor revision could produce a profit figure.

Performance requirement. The workbook must be generated and streamed within 10 seconds of request, satisfying NFR-06 and Objective 5.

# SECTION 5 — WORK BREAKDOWN STRUCTURE & 10-SPRINT ROADMAP

## 5.1 Sprint Schedule Table

### 5.1.1 Roadmap Overview

The project executes ten delivery sprints across a 137-day (19.5-week) academic window from 3 August 2026 to 18 December 2026. Sprints are two weeks in duration except Sprint 9 and Sprint 10, which are adjusted to honour the 27 November feature freeze and the 18 December academic deadline.

The methodology synthesises four frameworks, each confined to a distinct functional domain to prevent methodological ambiguity:

•  Waterfall Governance (SDLC) governs macro-level academic milestone verification, stage-gate approvals, documentation control, and formal submission deadlines.

•  Agile Scrum governs software construction in two-week iterative cycles, managing the feature backlog, rapid prototyping, and defect correction.

•  User-Centered Design (UCD) governs interface engineering, prioritising oversized touch targets, high visual contrast, and tap-count minimisation for fast-paced barista order entry.

•  ISO/IEC 25010 Quality Model establishes the benchmarking framework for functional suitability, operational reliability, performance efficiency, and security.

### 5.1.2 Sprint Summary

| Sprint | Dates | Days | Phase | Primary Outcome | Gate |
| --- | --- | --- | --- | --- | --- |
| S1 | 3 Aug – 16 Aug 2026 | 14 | P1 Problem Domain & Requirements | Requirements baseline and prioritised problem statement established | G1 — 14 Aug |
| S2 | 17 Aug – 30 Aug 2026 | 14 | P2 Architecture & Data Design | Nine-table schema and LAN topology specified | G2 — 28 Aug |
| S3 | 31 Aug – 13 Sep 2026 | 14 | P3 UI Foundations & Client Scaffold | React 19 SPA scaffold and design tokens operational | G3 — 4 Sep |
| S4 | 14 Sep – 27 Sep 2026 | 14 | P4 Security Foundation & Cloud Removal | API session/RBAC engine live; cloud dependency removed | G4 — 25 Sep |
| S5 | 28 Sep – 11 Oct 2026 | 14 | P5 Master Data & Specification | CRUD complete; SRS and test plan authored | G5 — 9 Oct |
| S6 | 12 Oct – 25 Oct 2026 | 14 | P6 Core POS & Recipe Engine | POS, cart, and atomic deduction with ledger committed | G6 — 23 Oct |
| S7 | 26 Oct – 8 Nov 2026 | 14 | P7 Alerting & Offline Resilience | Low-stock alerting and IndexedDB idempotency queue live | G7 — 6 Nov |
| S8 | 9 Nov – 22 Nov 2026 | 14 | P8 Recovery Ingestion & Reporting | USB/CSV ingestion and four-tab PhpSpreadsheet export live | G8 — 20 Nov |
| S9 | 23 Nov – 6 Dec 2026 | 14 | P9 Verification, Freeze & Burn-down | T01–T14 executed; feature freeze 27 Nov; defects burned down | G9 — 27 Nov (freeze) |
| S10 | 7 Dec – 18 Dec 2026 | 12 | P10 Deployment, Training & Acceptance | Production deployment, training, UAT and academic sign-off | G10 — 11 Dec · G11 — 18 Dec |

Note on sprint boundaries. The 27 November feature freeze falls on day 5 of Sprint 9. Sprint 9 therefore has a dual character: days 1–5 complete verification and impose the freeze, and days 6–14 are dedicated exclusively to defect burn-down against frozen scope. Sprint 10 carries Handover (7–11 December) and Acceptance (14–18 December).

### 5.1.3 Sprint 1 — Problem Domain & Requirements (3–16 August 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Conduct on-site operational study at a TravelBean MNL pop-up setup | Research | Z. Zapico | R. Gregorio | 7 Aug |
| 1.2 | Execute SWOT analysis and priority scoring matrix | Research | R. Gregorio | J. Roquid | 11 Aug |
| 1.3 | Construct fishbone cause-and-effect problem stratification | Research | R. Gregorio | J. Roquid | 11 Aug |
| 1.4 | Formalise functional and non-functional requirements (FR-01…FR-09, NFR-01…NFR-08) | Docs | R. Gregorio | Z. Zapico | 13 Aug |
| 1.5 | Author and finalise Project Plan and Project Charter | Docs | Z. Zapico | R. Gregorio | 14 Aug |

Gate G1 (14 August) — Requirements Baseline Accepted. Passes when: the problem statement is prioritised with numeric scores; all nine functional and eight non-functional requirements are numbered and traceable to an objective; and the Project Plan is approved by the Project Manager and System Analyst.

### 5.1.4 Sprint 2 — Architecture & Data Design (17–30 August 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Specify local Wi-Fi star network topology (192.168.137.x, host static .1, clients .100+) | Docs | R. Gregorio | Z. Zapico | 21 Aug |
| 2.2 | Design and execute the nine-table MySQL ERD and DDL script | MySQL | Z. Zapico | R. Gregorio | 28 Aug |
| 2.3 | Author ADR-001 architecture decision record | Docs | Z. Zapico | R. Gregorio | 28 Aug |
| 2.4 | Conduct architectural design review with academic evaluators | Docs | Team CTRL + STAY | Faculty | 28 Aug |

Gate G2 (28 August) — Schema and Topology Frozen. Passes when: SELECT COUNT(*) FROM information_schema.tables WHERE table_schema='venuevue_db' returns 10 (nine core tables plus api_sessions); the UNIQUE KEY uq_orders_client_txn index exists on orders.client_transaction_id; orders.event_id, orders.payment_method, and ingredients.unit_cost all exist; and every foreign key constraint is present and valid.

### 5.1.5 Sprint 3 — UI Foundations & Client Scaffold (31 August – 13 September 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Establish UI design tokens (48px+ touch targets, contrast, spacing scale) | Tailwind CSS 4 | R. Gregorio | J. Roquid | 4 Sep |
| 3.2 | Scaffold the React 19 + TanStack Router + Vite 8 SPA served by Apache | React / Vite | Z. Zapico | J. Roquid | 4 Sep |
| 3.3 | Configure build output for single-source deployment to htdocs | Vite / Apache | Z. Zapico | R. Gregorio | 4 Sep |

Gate G3 (4 September) — Client Scaffold Operational. Passes when: the compiled SPA loads in Chrome and Safari on a physical tablet over the LAN address; design tokens are applied consistently; and a rebuilt dist/ folder updates every connected tablet on browser refresh.

### 5.1.6 Sprint 4 — Security Foundation & Cloud Removal (14–27 September 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Implement auth.php with password_verify(), token issuance, and api_sessions persistence | PHP 8 | Z. Zapico | R. Gregorio | 25 Sep |
| 4.2 | Implement server-side session validation and RBAC middleware across all endpoints | PHP 8 | Z. Zapico | R. Gregorio | 25 Sep |
| 4.3 | Remove all Supabase dependencies and rebase data access onto the local PHP API | React / PHP | Z. Zapico | J. Roquid | 25 Sep |
| 4.4 | Build interactive Figma wireframes for seven core screens | Figma | R. Gregorio | J. Roquid | 25 Sep |
| 4.5 | Verify PWA/service-worker behaviour and IndexedDB queue on physical tablets over the LAN IP | QA | J. Roquid | R. Gregorio | 25 Sep |

Gate G4 (25 September) — Security Foundation Verified. Passes when: login returns a session token; an unauthenticated POST to sync.php returns HTTP 401; a BARISTA calling a stock-edit endpoint returns HTTP 403 and writes an audit_logs row; zero Supabase calls appear in the build manifest or at runtime; and the IndexedDB queue is demonstrably functional on a physical tablet over http://192.168.137.x.

Known schedule pressure. At the time of writing, authentication routing is already five days past its predecessor target and sits on the zero-float critical path. The de-scoping trigger in §5.2 applies if G4 slips beyond 2 October.

### 5.1.7 Sprint 5 — Master Data & Specification (28 September – 11 October 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Product, Ingredient, Recipe, and Event CRUD modules | React / PHP | R. Gregorio | Z. Zapico | 9 Oct |
| 5.2 | Client master data load: menu, recipes, ingredient costs, and event schedule | Data | J. Roquid | Client | 9 Oct |
| 5.3 | Author the Software Requirements Specification (SRS) | Docs | R. Gregorio | Z. Zapico | 9 Oct |
| 5.4 | Author the T01–T14 test plan (moved forward from Sprint 9) | Docs | R. Gregorio | Z. Zapico | 9 Oct |

Gate G5 (9 October) — Master Data and Specification Complete. Passes when: CRUD round-trips succeed for products, ingredients, recipe mappings, and events; the client's real menu, recipes, and unit costs are loaded and reconciled against the client's records; the SRS exists with a complete traceability matrix; and the T01–T14 test plan is written and reviewed.

Schedule rationale. Authoring the test plan in Sprint 5 rather than Sprint 9 is the single highest-leverage schedule intervention available. Tests written alongside the engine are executable the day the engine lands, converting end-loaded verification risk into continuous verification and recovering approximately two weeks of contingency on a zero-float chain.

### 5.1.8 Sprint 6 — Core POS & Recipe Engine (12–25 October 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Touch POS ordering grid with category tab filtering and single-tap selection | React | Z. Zapico | J. Roquid | 16 Oct |
| 6.2 | Cart engine with real-time totals and cash change calculation | React | Z. Zapico | J. Roquid | 16 Oct |
| 6.3 | Atomic recipe deduction engine with SELECT … FOR UPDATE row locking | PHP / PDO | Z. Zapico | R. Gregorio | 23 Oct |
| 6.4 | inventory_transactions ledger writes on every deduction | PHP / PDO | Z. Zapico | R. Gregorio | 23 Oct |
| 6.5 | Negative and zero quantity rejection with HTTP 422 | PHP | Z. Zapico | R. Gregorio | 23 Oct |
| 6.6 | Begin executing T01, T02 and T03 against the committed engine | QA | J. Roquid | R. Gregorio | 23 Oct |

Gate G6 (23 October) — Core Transactional Integrity Proven. Passes when: a single order commits with the correct server-resolved total and change; inventory_transactions gains exactly one SALE row per ingredient affected; a payload containing a negative quantity is rejected with HTTP 422 and leaves stock unchanged; and two tablets submitting concurrently produce zero lost updates.

### 5.1.9 Sprint 7 — Alerting & Offline Resilience (26 October – 8 November 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Low-stock alert badges and Owner-only restock dashboard | React / PHP | J. Roquid | R. Gregorio | 30 Oct |
| 7.2 | IndexedDB PENDING_LOCAL transaction queue | React | Z. Zapico | J. Roquid | 6 Nov |
| 7.3 | UUIDv4 idempotency engine end-to-end (client mint through server UNIQUE enforcement) | React / PHP | Z. Zapico | J. Roquid | 6 Nov |
| 7.4 | IndexedDB quota monitoring and storage-exhaustion handling | React | J. Roquid | Z. Zapico | 6 Nov |
| 7.5 | Bounded exponential-backoff retry with durable failure state | React | Z. Zapico | J. Roquid | 6 Nov |

Gate G7 (6 November) — Offline Resilience Verified. Passes when: killing the server mid-checkout leaves the order durably PENDING_LOCAL; on restoration it reconciles automatically; replaying the identical UUID creates no second order; and quota-exhaustion handling surfaces a warning and prompts export before data loss can occur.

### 5.1.10 Sprint 8 — Recovery Ingestion & Reporting Engine (9–22 November 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 8.1 | USB recovery-package export and administrative import module | PHP / React | Z. Zapico | J. Roquid | 13 Nov |
| 8.2 | Manual Excel/CSV batch ingestion engine with atomic rollback | PhpSpreadsheet / PHP | Z. Zapico | J. Roquid | 13 Nov |
| 8.3 | PhpSpreadsheet Tab 1 (Summary — event, gross revenue, COGS, net profit, AOV, payment distribution) | PhpSpreadsheet | J. Roquid | Z. Zapico | 13 Nov |
| 8.4 | PhpSpreadsheet Tab 2 (Sales by Product) | PhpSpreadsheet | J. Roquid | Z. Zapico | 13 Nov |
| 8.5 | PhpSpreadsheet Tab 3 (Ingredient Usage) and Tab 4 (Restock List) with formatting and styling | PhpSpreadsheet | J. Roquid | R. Gregorio | 20 Nov |
| 8.6 | Automated daily .sql dump with USB mirror (restores NFR-04) | Ops / PHP | Z. Zapico | R. Gregorio | 20 Nov |

Gate G8 (20 November) — Reporting Engine Delivered. Passes when: a four-tab .xlsx workbook is generated in ≤ 10 seconds; Tab 1 reports event name, date, duration, gross revenue, cost of goods sold and net profit for a closed event; Tabs 3 and 4 reconcile against inventory_transactions; a CSV batch import commits valid rows atomically and rolls back entirely on a malformed row; and a daily .sql dump exists on both the host drive and the USB mirror.

Schedule rationale. Phase 8 is deliberately split across the sprint boundary so that a failure in Tabs 3–4 cannot consume the whole verification window. Tabs 1–2 land on 13 November; Tabs 3–4 and the backup utility land on 20 November.

### 5.1.11 Sprint 9 — Verification, Freeze & Burn-down (23 November – 6 December 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 9.1 | Execute scenarios T04–T08 (partition, recovery, duplicate replay, CSV import) | QA | J. Roquid | R. Gregorio | 27 Nov |
| 9.2 | Execute scenarios T09–T14 (stock conflict, RBAC, session expiry, BOM accuracy, alert accuracy, export latency) | QA | J. Roquid | R. Gregorio | 27 Nov |
| 9.3 | Consolidate execution logs, compute A_deduction, R_sync, R_duplicate, L_trans | QA | J. Roquid | R. Gregorio | 27 Nov |
| 9.4 | FEATURE FREEZE — scope locked | Governance | Z. Zapico | — | 27 Nov |
| 9.5 | Defect burn-down against frozen scope only | All | Team CTRL + STAY | R. Gregorio | 6 Dec |
| 9.6 | Author User Operational Manual and System Installation Guide | Docs | R. Gregorio | J. Roquid | 4 Dec |
| 9.7 | Configure production host hardware and Windows Mobile Hotspot | Ops | Z. Zapico | J. Roquid | 4 Dec |

Gate G9 (27 November) — Feature Freeze and Verification Complete. Passes when: all fourteen scenarios T01–T14 have been executed and pass; A_deduction = 100%; R_sync = 100%; R_duplicate = 0%; the 95th-percentile L_trans ≤ 500 ms; zero Priority 1 or Priority 2 defects remain open; and no new feature enters development after this date.

### 5.1.12 Sprint 10 — Deployment, Training & Acceptance (7–18 December 2026)

| # | Task | Component | Owner | Independent Reviewer | Target |
| --- | --- | --- | --- | --- | --- |
| 10.1 | Deploy the final production stack onto the client host laptop | Ops | Z. Zapico | J. Roquid | 11 Dec |
| 10.2 | Conduct hands-on training for TravelBean MNL baristas and owners | Ops | J. Roquid | Client | 11 Dec |
| 10.3 | Deliver User Operational Manual and System Installation Guide to the client | Docs | R. Gregorio | J. Roquid | 11 Dec |
| 10.4 | Execute User Acceptance Testing scripts with the client | QA | J. Roquid | Client | 18 Dec |
| 10.5 | Secure signed formal acceptance from the client and the university board | Governance | Z. Zapico | Client & Faculty | 18 Dec |
| 10.6 | Finalise the thesis manuscript and prepare the oral defence | Docs | Team CTRL + STAY | Faculty | 18 Dec |
| 10.7 | Commence the six-month post-turnover support window (LoA §3.1.3) | Ops | Z. Zapico | — | 18 Jun 2027 |

Gates G10 (11 December) and G11 (18 December). G10 passes on successful production deployment, completed training, and delivered manuals. G11 passes on a signed UAT acceptance certificate, a signed client and academic acceptance record, and submitted final manuscript.

### 5.1.13 Consolidated Milestone Gate Register

| Gate | Date | Criterion Summary |
| --- | --- | --- |
| G1 | 14 Aug 2026 | Requirements baseline accepted; FR/NFR numbered and traceable. |
| G2 | 28 Aug 2026 | Nine-table schema executed; constraints and keys verified; topology frozen. |
| G3 | 4 Sep 2026 | React SPA scaffold loads on physical tablets over LAN; tokens applied. |
| G4 | 25 Sep 2026 | Auth and RBAC enforced (401/403); Supabase removed; IndexedDB verified on device. |
| G5 | 9 Oct 2026 | Master data CRUD complete; client data loaded; SRS and test plan authored. |
| G6 | 23 Oct 2026 | Atomic deduction with ledger; negative quantity rejected; zero lost updates. |
| G7 | 6 Nov 2026 | Offline queue, idempotency, backoff retry, and quota handling verified. |
| G8 | 20 Nov 2026 | Four-tab workbook ≤ 10 s with event/profit Tab 1; atomic batch import; daily backup. |
| G9 | 27 Nov 2026 | T01–T14 all pass; metric targets met; FEATURE FREEZE. |
| G10 | 11 Dec 2026 | Production deployed; training delivered; manuals handed over. |
| G11 | 18 Dec 2026 | UAT signed; client and academic acceptance secured; manuscript submitted. |

## 5.2 Feature Freeze & Critical Path

### 5.2.1 Feature Freeze Declaration

Friday, 27 November 2026 is the immutable feature freeze for VenueVue Revision 2.3.

From 27 November 2026 onward, no new functional capability, no additional report tab, no new data entity, no new endpoint, no interface redesign, and no architectural change may enter development. Work after the freeze is restricted to exactly four categories:

1. Defect correction against already-frozen functionality.

2. Deployment of the frozen build to the client host.

3. Documentation — the User Operational Manual and System Installation Guide.

4. Training and User Acceptance Testing.

Any proposal for post-freeze scope addition must be rejected by the Project Manager regardless of its merit, and deferred to the post-turnover support window or to a future project phase. This rule exists because the residual three-week window is the project's only buffer; consuming it with new work removes all protection from the 18 December academic deadline.

### 5.2.2 Critical Path

9-table DDL ──► API Auth/RBAC ──► Recipe Deduction ──► Idempotency ──► Export Engine ──► T01–T14 ──► FREEZE

(G2)             (G4)               (G6)               (G7)             (G8)          (G9)

28 Aug           25 Sep             23 Oct              6 Nov           20 Nov        27 Nov

│                                    │

└──► Master Data (G5) ──► POS Grid ───┘

9 Oct            16 Oct

Critical path narrative. The chain runs from the database schema through the security foundation, into the recipe deduction engine, through idempotency and the offline queue, into the reporting engine, and terminates in full verification at the freeze. Two branches feed it: master data CRUD must complete before the POS grid can be built against real menu data, and the deduction engine cannot be validated until CRUD provides recipes. No task on this chain can be deferred, parallelised away, or shortened without moving the freeze date.

### 5.2.3 Zero-Float Analysis

Float is the amount of delay a task may absorb before it delays the project end date. The audit of predecessor revisions established that the schedule contained no float anywhere prior to the freeze. This condition is unchanged and is stated here explicitly so that it is managed rather than discovered.

| Critical Segment | Window | Duration | Float |
| --- | --- | --- | --- |
| G2 → G4 | 28 Aug → 25 Sep 2026 | 4 weeks | 0 |
| G4 → G6 | 25 Sep → 23 Oct 2026 | 4 weeks | 0 |
| G6 → G7 | 23 Oct → 6 Nov 2026 | 2 weeks | 0 |
| G7 → G8 | 6 Nov → 20 Nov 2026 | 2 weeks | 0 |
| G8 → G9 (all fourteen scenarios) | 20 Nov → 27 Nov 2026 | 1 week | 0 |
| **G9 → G11 (reserved) | 27 Nov → 18 Dec 2026 | 3 weeks | 3 weeks — the only buffer |

Interpretation. Every segment from 28 August to 27 November is on a zero-float chain. A single day lost anywhere in that chain moves the freeze date by one day. Because the freeze cannot move (it is bounded by the 18 December academic deadline three weeks later), any slippage in the zero-float region must be recovered through de-scoping, not through rescheduling.

Residual risk statement. The three-week post-freeze reserve protects sign-off — deployment, training, documentation, UAT, and manuscript preparation — but it cannot absorb development slippage, because the freeze itself sits at the end of the zero-float chain. This is a structural property of the schedule, not a temporary condition, and it is the reason the interventions below are mandatory rather than advisory.

### 5.2.4 Mandatory Schedule Interventions

The following interventions are approved and are already reflected in §5.1. They exist to recover contingency on a chain that structurally has none.

| # | Intervention | Rationale | Effect |
| --- | --- | --- | --- |
| I-1 | Author the T01–T14 test plan in Sprint 5 (9 October), not Sprint 9. | Tests written alongside the engine are executable the day the engine lands. End-loaded verification is the dominant schedule risk. | Recovers approximately two weeks of contingency; converts verification from a one-week cliff into continuous practice. |
| I-2 | Begin executing T01–T03 immediately upon the recipe engine committing (23 October). | The three foundational scenarios validate the core transactional claim of the system. Discovering a defect in late November would leave no recovery path. | Removes roughly two weeks of end-loaded test risk. |
| I-3 | Split Phase 8 across two sprints. Tabs 1–2 by 13 November; Tabs 3–4 plus backup by 20 November. | A failure in the final two report tabs must not be able to consume the entire verification week. | Isolates reporting risk from verification capacity. |
| I-4 | Timebox gate G4. If the security foundation has not passed by 2 October 2026, invoke de-scoping. | G4 already carries five days of slippage at baseline and gates the entire critical path. | Bounds the blast radius of the highest-risk gate. |
| I-5 | Pre-agreed de-scoping order. | De-scoping decisions made under time pressure and without a pre-agreed order produce arbitrary loss of value. | See §5.2.5. |

### 5.2.5 Pre-Agreed De-Scoping Order

If the zero-float chain forces de-scoping, items are cut in the following order. The sequence is deliberately arranged so that the lowest client value is sacrificed first and no cut touches the client's headline requirement.

| Order | Item De-Scoped | Justification | Objectives Preserved |
| --- | --- | --- | --- |
| 1 | PDF report export | Never in scope. Approved reporting is the four-tab .xlsx workbook only; the Letter of Agreement reference to PDF is struck by §6.2. No requirement depends on it. | All |
| 2 | Mechanism 3 — Manual Excel/CSV batch ingestion | Least-used of the three ingestion mechanisms. Mechanisms 1 and 2 fully satisfy the objective, and a USB JSON recovery package already provides the physical fallback. | 1, 2, 3, 4, 6, 7, 8 |
| 3 | Multi-tablet concurrency testing beyond two devices | The client operates with at most three tablets. Two-device concurrency testing exercises the same row-locking path. | All |
| 4 | Cosmetic interface polish and theming | Presentation refinement carries no functional or contractual obligation. | All |

Protected items — never de-scoped. The following may not be cut under any schedule pressure, because each is either a contractual obligation or the client's headline requirement:

•  The nine-table schema, in particular EVENTS, ORDERS.event_id, ORDERS.payment_method, and INGREDIENTS.unit_cost.

•  Tab 1 of the workbook with per-event net profit — the client's Priority Rank 5 requirement and the primary client-facing value of the engagement.

•  UUIDv4 idempotency — without it, duplicate orders and duplicate stock deductions are guaranteed.

•  API-level authentication and RBAC — without it, the ingest endpoint is open to any device on the hotspot.

•  Atomic deduction with row locking — without it, concurrent tablets corrupt inventory.

•  The 27 November feature freeze.

### 5.2.6 Effort Distribution and Budget Baseline

The project is budgeted at 650 total development hours across the 19.5-week window, distributed as follows:

| Personnel | Allocated Hours | Imputed Rate | Imputed Valuation |
| --- | --- | --- | --- |
| Zapico, Zaki — Project Manager / Lead Developer | 250 | ₱250/hr | ₱62,500.00 |
| Gregorio, Rhea Mae — System Analyst / QA Lead | 220 | ₱200/hr | ₱44,000.00 |
| Roquid, Jenny Lyn — QA & Testing Specialist | 180 | ₱180/hr | ₱32,400.00 |
| Total Imputed Team Labour Valuation | 650 | — | ₱138,900.00 |

| Budget Category | Direct Out-of-Pocket Cost | Imputed Project Valuation |
| --- | --- | --- |
| Software Development and Licences (React 19, TanStack Router, Vite 8, Tailwind CSS 4, PHP 8.x, MySQL 8.x, XAMPP, PhpSpreadsheet — all open source) | ₱0.00 | ₱0.00 |
| Hardware and Storage Media (two 64GB USB flash drives for offline database backup) | ₱900.00 | ₱33,900.00 (includes client-supplied hardware) |
| Software Engineering Labour (CTRL + STAY) | ₱0.00 | ₱138,900.00 |
| Operational and Deployment Outlays (client site travel to Tondo, Manila; documentation printing and binding; deployment testing supplies; contingency buffer) | ₱10,700.00 | ₱10,700.00 |
| TOTAL PROJECTED EXPENDITURE | ₱11,600.00 | ₱183,500.00 |

Effort feasibility note. The 250-hour allocation to the Lead Developer equates to approximately 33 hours per week sustained across 19.5 weeks. This is achievable for a student team only if the three-way parallel implementation split is eliminated. At the time of audit, three separate client implementations existed simultaneously — two Flutter codebases and one React application. Ratifying ADR-001 and archiving the Flutter trees is therefore not merely an architectural preference; it is the precondition that makes the effort budget attainable. With three implementations in flight, 650 hours is insufficient; with one, it is sufficient with margin.

Re-costing note. The ₱11,600.00 and ₱183,500.00 figures, the 650-hour allocation, and the ₱8,000.00 tablet valuation were inherited unchanged from the Software Engineering I plan and carried forward through materially larger scope — through a front-end stack replacement, a schema expansion from six to nine tables, the addition of UUID idempotency and row-level locking, and a fourteen-scenario test matrix. The 33,900.00 hardware valuation also predates the expansion from one to three client tablets. These figures are retained here as the approved baseline but must be re-costed upon approval of the nine-table scope, and the re-costed schedule presented at gate G5.

# SECTION 6 — RISK MANAGEMENT, COMPLIANCE & LEGAL ALIGNMENT

## 6.1 Critical Risk Assessment & Mitigation Matrix

### 6.1.1 Risk Register Summary

The following register records every critical risk identified by the comprehensive audit of predecessor revisions, together with the mitigation applied in Revision 2.3 and the contingency to be invoked if the mitigation proves insufficient. Likelihood and impact are assessed on a three-point scale (Low, Medium, High); severity is the combination of the two.

| ID | Risk | Likelihood | Impact | Severity | Mitigation Status |
| --- | --- | --- | --- | --- | --- |
| CR-00 | All source code exists only in the Recycle Bin | Medium | Critical | Critical | Open — immediate action required |
| CR-01 | Order sync non-functional: client and server contracts incompatible | Certain | Critical | Critical | Resolved by Rev 2.3 contract |
| CR-02 | API has no authentication or authorization | Certain | Critical | Critical | Resolved by Rev 2.3 engine |
| CR-03 | Schema incomplete: 6 of 9 required tables; no idempotency column | Certain | High | Critical | Resolved by Rev 2.3 DDL |
| CR-04 | PhpSpreadsheet reporting module 0% implemented | Certain | High | Critical | Scheduled — Sprints 8 |
| CR-05 | Hosted cloud dependency contradicts the project premise | Certain | High | Critical | Resolved by ADR-001; removed in Sprint 4 |
| CR-06 | Zero schedule float; single slip loses the deadline | High | High | Critical | Mitigated by I-1…I-5 |
| CR-07 | Three parallel client implementations by a three-person team | Certain | High | Critical | Resolved by ADR-001 |
| CR-08 | .env committed to a public repository | Certain | Medium | High | Open — immediate action required |
| CR-09 | No event entity and no ingredient cost; client's headline ask unbuildable | Certain | High | Critical | Resolved by 9-table DDL |
| CR-10 | Negative quantity accepted, inflating recorded stock | High | Medium | High | Resolved by Rev 2.3 engine |
| CR-11 | Every order attributed to user ID 1 | Certain | Medium | High | Resolved by session-derived identity |
| CR-12 | Prototype client crashes on launch; checkout orphans line items | Certain | Medium | Medium | Resolved by ADR-001 retirement |

### 6.1.2 Detailed Risk Entries

CR-00 — Source Code Exists Only in the Recycle Bin

| Attribute | Detail |
| --- | --- |
| Description | Both project source folders — the Flutter client trees and the directory containing the only PHP backend and the only DDL script — were moved to the operating system Recycle Bin during the audit window. They were absent from both the workspace and the entire user profile, and were located only in C:\$Recycle.Bin\. |
| Likelihood / Impact | Medium / Critical |
| Consequence if realised | Permanent loss of the PHP backend engine, the SQL schema, and both client codebases. Recovery would require reconstruction from the specifications in this document, costing an estimated two to three weeks on a zero-float chain — which would consume the entire post-freeze reserve and jeopardise the academic deadline. |
| Prevention (immediate) | Restore both folders from the Recycle Bin. Commit all source to the project Git repository on a protected branch. Establish a documented backup regime with at least two independent locations. |
| Contingency | If already lost, reconstruct the backend from §4.2 and the schema from §3.2, both of which are complete and executable specifications. Rebuild the client from the ratified React 19 specification. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any source artefact not present in a committed Git branch. |
| Status | OPEN — action required before any further development. |

CR-01 — Order Sync Non-Functional Due to Contract Incompatibility

| Attribute | Detail |
| --- | --- |
| Description | Both client implementations transmitted a flat order map, while the backend required a nested {"order": {…}} envelope and rejected all such requests with HTTP 400. Neither client ever transmitted the items array the backend required. The observed effect was a 0% sync success rate: no order ever reached MySQL and no inventory was ever deducted server-side. |
| Likelihood / Impact | Certain (already realised) / Critical |
| Consequence if realised | The project's highest-priority client problem remains unsolved. Objectives 1, 2, and 6 all fail. The system would present as functional while silently discarding every transaction. |
| Prevention | The wire contract is frozen in §4.1 as a single normative artefact. Both the client envelope builder and the server parser are specified against it. Contract conformance is a gate condition at G4, G6, and G8, and is exercised continuously by scenarios T01–T08. |
| Contingency | Contract conformance is verified by a single end-to-end integration test executed before any other verification. If it fails, no other testing proceeds until it passes. |
| Owner | Zapico, Zaki (implementation); Gregorio, Rhea Mae (verification) |
| Trigger / Indicator | Any HTTP 400 or HTTP 422 response during a controlled sync test using a known-valid payload. |
| Status | RESOLVED by the Revision 2.3 contract and engine. |

CR-02 — API Has No Authentication or Authorization

| Attribute | Detail |
| --- | --- |
| Description | The predecessor backend performed no session validation, no role check, and no token verification, and emitted Access-Control-Allow-Origin: *. Any device that joined the hotspot — including a customer's telephone — could create orders, set an arbitrary user_id, and manipulate inventory. |
| Likelihood / Impact | Certain (already realised) / Critical |
| Consequence if realised | Inventory and revenue records are untrustworthy. Objective 7 and scenarios T10 and T11 cannot pass. The Data Privacy Act control promised in the Letter of Agreement is breached. Cash-handling accountability is impossible. |
| Prevention | Bearer-token authentication on every request, with only SHA-256 hashes stored in api_sessions. Session-derived user identity, so user_id is never accepted from the client. CORS restricted to the application origin. Every authorization denial written to audit_logs. |
| Contingency | If the token mechanism is unavailable, the endpoint is disabled entirely rather than operated unauthenticated. An open order-ingest endpoint on a shared hotspot is never an acceptable interim state. |
| Owner | Zapico, Zaki (implementation); Gregorio, Rhea Mae (verification) |
| Trigger / Indicator | Any successful POST to sync.php without a valid bearer token. |
| Status | RESOLVED by the Revision 2.3 engine; verified at gate G4. |

CR-03 — Schema Incomplete and Lacking Idempotency Surface

| Attribute | Detail |
| --- | --- |
| Description | The executed DDL contained six tables rather than the documented eight, omitting inventory_transactions and audit_logs. The orders table contained no client_transaction_id column and no uniqueness constraint of any kind, so the database could not reject a replayed transaction. Documented column names differed from implemented names throughout, and products lacked a category column despite a category-filtering requirement. |
| Likelihood / Impact | Certain (already realised) / High |
| Consequence if realised | No inventory traceability, no security audit trail, and no idempotency enforcement — making the R_duplicate = 0% objective structurally unachievable. |
| Prevention | The nine-table DDL in §3.2 is the single normative schema, with column names reconciled to the documented vocabulary and post-migration verification queries provided. Gate G2 requires the verification queries to pass before any dependent work begins. |
| Contingency | Because the schema is frozen at G2 and every later artefact depends upon it, a schema defect discovered after G2 requires a migration script and re-verification of all scenarios. This is why G2 is an explicit gate rather than an informal checkpoint. |
| Owner | Zapico, Zaki (implementation); Gregorio, Rhea Mae (verification) |
| Trigger / Indicator | information_schema count differing from 10; absence of uq_orders_client_txn. |
| Status | RESOLVED by the Revision 2.3 DDL. |

CR-04 — Reporting Module 0% Implemented

| Attribute | Detail |
| --- | --- |
| Description | No PhpSpreadsheet code existed anywhere. The only PHP file in either source tree was the ingest endpoint, which offered no read or aggregation path. There was no composer.json, no vendor/ directory, and no .xlsx file on disk. The project's headline client-facing deliverable — the four-tab workbook replacing two to three hours of manual tallying — existed only as prose in planning documents. |
| Likelihood / Impact | Certain (already realised) / High |
| Consequence if realised | Objective 5, FR-07, Objective 8, and scenario T14 all fail. The primary tangible client benefit of the engagement is not delivered. |
| Prevention | The reporting engine is decomposed into four discrete sub-tasks across Sprint 8, each with a named independent reviewer, so that no single task carries the whole deliverable. Tab 1 depends on the schema additions made in Revision 2.3 and cannot be attempted before gate G5. |
| Contingency | If PhpSpreadsheet integration proves infeasible within the sprint, the fallback is server-generated CSV per tab, assembled into a workbook by the client's existing Excel installation. This preserves the analytical content while sacrificing the pre-formatted single-file convenience, and is treated as a formal de-scope requiring Project Manager approval. |
| Owner | Roquid, Jenny Lyn (implementation); Gregorio, Rhea Mae (verification) |
| Trigger / Indicator | G8 not achieved by 20 November 2026. |
| Status | SCHEDULED — Sprint 8, gates G8. |

CR-05 — Cloud Dependency Contradicts the Project Premise

| Attribute | Detail |
| --- | --- |
| Description | The React prototype implementation depended on Supabase — hosted PostgreSQL with GoTrue authentication, accessed over the public internet. The word "Supabase" appears in none of the approved project documents. No PHP, MySQL, Apache, or LAN code existed in that implementation. |
| Likelihood / Impact | Certain (already realised) / High |
| Consequence if realised | The system is unusable at precisely the venues for which it was commissioned, falsifying the project's central premise and breaching Letter of Agreement §1.1's requirement for a standalone local server environment. The academic demonstration becomes contingent on connectivity the venue may not provide. Client operational and financial data leave the client's premises without a Data Sharing Agreement. |
| Prevention | ADR-001 is binding and expressly excludes hosted services. Supabase is removed in Sprint 4. Compliance is verified at every gate by monitoring for outbound WAN traffic during a complete sales cycle, which must show zero calls. |
| Contingency | If any cloud dependency is discovered in a build, the build is rejected at the gate and cannot proceed. There is no acceptable interim state in which the delivered system contacts a hosted service. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any outbound WAN request during a monitored sales cycle; presence of a cloud SDK in the build manifest. |
| Status | RESOLVED by ADR-001; removal executed in Sprint 4. |

CR-06 — Zero Schedule Float

| Attribute | Detail |
| --- | --- |
| Description | Every task from 28 August to 27 November 2026 lies on a zero-float critical path. All fourteen verification scenarios are allocated a single week. The only three-week reserve sits entirely after the freeze and therefore protects sign-off but cannot absorb development slippage. |
| Likelihood / Impact | High / High |
| Consequence if realised | Any single overrun in the zero-float region consumes the pre-freeze contingency that does not exist, and must be recovered by cutting scope or by moving the freeze — the latter being blocked by the 18 December academic deadline. |
| Prevention | Five mandatory interventions (I-1 to I-5, §5.2.4): test plan authored in Sprint 5; T01–T03 executed from 23 October; Phase 8 split across two sprints; G4 timeboxed to 2 October; and a pre-agreed de-scoping order. |
| Contingency | Execute the de-scoping order in §5.2.5, beginning with PDF export, then Mechanism 3, then extended multi-tablet testing, then cosmetic polish. Protected items are never cut. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any gate G4 through G8 missed by more than five working days. |
| Status | MITIGATED — interventions approved and embedded in §5.1. |

CR-07 — Three Parallel Client Implementations

| Attribute | Detail |
| --- | --- |
| Description | Three separate client implementations existed simultaneously: two independent Flutter codebases totalling approximately 1,800 lines of Dart, and one React application. The two Flutter trees shared no code and neither referenced the other. Effort was divided three ways, and no single artefact was complete. |
| Likelihood / Impact | Certain (already realised) / High |
| Consequence if realised | The 650-hour effort budget becomes unattainable, since it was costed for a single implementation. Progress is fragmented across artefacts and none reaches completion. This is the primary root cause of the project's assessed 12–15% completion against a 38% elapsed timeline. |
| Prevention | ADR-001 ratifies the React 19 client as the sole implementation path and retires both Flutter trees to archive/flutter-prototype with no further development. The archived code is retained only as interface design reference. |
| Contingency | If the React path is later found unviable, the working Flutter slice (the leaner venuevue_mobile codebase, which carries correct provider wiring and functional checkout) provides a known-good reference for reconstruction. The non-functional Flutter codebase carries no such value and should not be used. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any commit to a Flutter tree after ADR-001 ratification. |
| Status | RESOLVED by ADR-001. |

CR-08 — `.env` Committed to a Public Repository

| Attribute | Detail |
| --- | --- |
| Description | The prototype repository contained a .env file that was not excluded by .gitignore and had been committed and pushed to a public GitHub repository. The file defined six variables including the Supabase project reference and publishable key. A database migration in the same repository seeded three demonstration accounts with hardcoded passwords into the authentication table. |
| Likelihood / Impact | Certain (already realised) / Medium |
| Consequence if realised | The committed values comprise the project URL, project reference, and the publishable (anonymous) key, which is client-exposed by design. No privileged service-role key was present. Residual risk is therefore moderate but real, and is amplified by the seeded demonstration accounts with known passwords and by the fact that an anonymous key is only as safe as its row-level security policy. |
| Prevention | Rotate the publishable key. Add .env and .dev.vars to .gitignore. Remove the file from version control with git rm --cached .env, then rotate the credential so the historical commit is worthless. Purge the three seeded demonstration accounts. Adopt the project-wide rule that no credential, connection string, or token is ever committed. |
| Contingency | If a privileged key is later found to have been committed, rotate immediately and audit the provider's access log for unauthorised use. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any .env, .dev.vars, credential, or connection string present in a tracked file. |
| Status | OPEN — action required. |

CR-09 — No Event Entity and No Ingredient Cost

| Attribute | Detail |
| --- | --- |
| Description | Neither the six-table nor the eight-table schema contained an EVENTS table, an ORDERS.event_id association, or any ingredient cost field. The product is named VenueVue, the client's fifth-ranked problem is the absence of historical event performance data, and the contractual report specification defines Tab 1 as containing "Event Name, Date, Duration … Net Profit Estimates … Primary Payment Distribution." |
| Likelihood / Impact | Certain (already realised) / High |
| Consequence if realised | The client's headline requirement cannot be satisfied. Per-event revenue, per-event product mix, high-margin-event identification, cost of goods sold, and net profit are all structurally impossible. Four of the workbook's defining elements — event name, duration, net profit, and payment distribution — have no data source. |
| Prevention | Revision 2.3 expands the core schema to nine tables, adding EVENTS, ORDERS.event_id, ORDERS.payment_method, and INGREDIENTS.unit_cost. These four additions are classified as protected scope in §5.2.5 and may not be de-scoped under any schedule pressure. |
| Contingency | If event-level attribution is somehow unavailable for a given order, event_id is nullable and the order is retained as unattributed, so no financial record is lost. Explicit zero-value rows are reported for closed events with no orders rather than omitting them, preserving the 100% coverage required by Objective 8. |
| Owner | Zapico, Zaki (schema); Gregorio, Rhea Mae (requirements verification) |
| Trigger / Indicator | Tab 1 failing to report event name, duration, or net profit for a closed event. |
| Status | RESOLVED by the Revision 2.3 nine-table DDL. |

CR-10 — Negative Quantity Accepted, Inflating Recorded Stock

| Attribute | Detail |
| --- | --- |
| Description | The predecessor backend validated line quantities using PHP's empty() construct. Because empty(-5) evaluates to false, a negative quantity passed validation, producing a negative line total, a reduced order total, and — critically — a negative deduction applied to the ingredient's stock level, which increased recorded inventory. |
| Likelihood / Impact | High / Medium |
| Consequence if realised | Silent inventory corruption. Stock levels diverge from physical reality, defeating the low-stock alerting that is the system's third-ranked purpose, and producing incorrect restock recommendations and cost of goods sold. |
| Prevention | Quantities are validated with FILTER_VALIDATE_INT against an explicit <= 0 rejection and a per-line maximum. Database-level CHECK (quantity > 0) constraints on both order_items and recipe_items provide defence in depth against any future code path. |
| Contingency | The inventory_transactions ledger makes any historical corruption detectable and correctable through an ADJUSTMENT transaction with a documented reason. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any inventory_transactions row with a positive quantity_delta and transaction_type = 'SALE'. |
| Status | RESOLVED by the Revision 2.3 engine and DDL constraints. |

CR-11 — Every Order Attributed to User ID 1

| Attribute | Detail |
| --- | --- |
| Description | Both client implementations hardcoded userId: 1 when constructing order records, and no login code existed in either client. Consequently every order, regardless of which member of staff was operating the device, was attributed to whichever account held identifier 1. |
| Likelihood / Impact | Certain (already realised) / Medium |
| Consequence if realised | Role-based access control is decorative. Sales cannot be attributed to staff for accountability purposes. Objective 7 is unmeasurable, and the security audit trail records a constant user for all activity. |
| Prevention | The server derives user_id exclusively from the validated session token; user_id is explicitly forbidden in the client payload (§4.1.4). The client acquires a session through auth.php and transmits no user identity of its own. |
| Contingency | Where historical attribution is required, the tablet_id recorded on every order provides device-level attribution as a partial substitute. |
| Owner | Zapico, Zaki (implementation); Roquid, Jenny Lyn (verification) |
| Trigger / Indicator | More than one distinct user_id never appearing in orders across a multi-staff test. |
| Status | RESOLVED by session-derived identity in the Revision 2.3 engine. |

CR-12 — Prototype Client Crashes on Launch and Orphans Line Items

| Attribute | Detail |
| --- | --- |
| Description | Of the two Flutter prototypes, the larger and structurally more ambitious codebase did not register its state-management provider at the application root, while its screens nonetheless requested that provider. Static analysis confirmed the unused provider import, and the application would throw a provider-not-found exception immediately on launch. Its checkout path additionally wrote line items with a literal order identifier of zero, without awaiting the insert, orphaning every line item. A 191-line checkout implementation in the same tree was dead code, never imported. |
| Likelihood / Impact | Certain (already realised) / Medium |
| Consequence if realised | The larger prototype cannot be demonstrated and cannot persist line items. Any attempt to present it as the deliverable would fail visibly during defence. |
| Prevention | ADR-001 retires both Flutter trees. If any Flutter code is ever revisited, only the leaner codebase — which carries correct provider registration, functional checkout, and correct currency — is used as reference. The non-functional tree is explicitly marked non-referenceable. |
| Contingency | None required, given retirement. |
| Owner | Zapico, Zaki |
| Trigger / Indicator | Any proposal to demonstrate or extend a Flutter prototype. |
| Status | RESOLVED by ADR-001 retirement. |

### 6.1.3 Risk Monitoring Cadence

| Activity | Frequency | Owner | Output |
| --- | --- | --- | --- |
| Risk register review | Every sprint gate | Zapico, Zaki | Updated likelihood/impact, new risks, closed risks |
| Open-defect triage against frozen scope | Daily during Sprint 9 | Roquid, Jenny Lyn | Defect register with priority classification |
| Critical-path schedule check | Weekly | Zapico, Zaki | Float consumption report; escalation if any gate slips beyond five working days |
| Security and credential hygiene audit | At G4, G8, G10 | Gregorio, Rhea Mae | Confirmation of no committed credentials and no outbound WAN calls |
| Backup verification | Weekly, then daily from G8 | Zapico, Zaki | Confirmed .sql dump present on host and USB mirror |

## 6.2 Legal & Contractual Alignments

### 6.2.1 Letter of Agreement — Required Amendments

The signed Letter of Agreement between CTRL + STAY and TravelBean MNL requires four specific amendments to bring it into alignment with this Project Plan and to remove a promise that was never in scope. These amendments must be executed as a written addendum signed by both parties.

| Location | Current Text | Required Amendment | Rationale |
| --- | --- | --- | --- |
| §1.2 | *"Generate automated end-of-event sales summaries, daily sales logs, and exportable Excel (.xlsx) or PDF performance reports."* | Strike the PDF alternative. Replace with: "Generate automated end-of-event sales summaries, daily sales logs, and exportable Excel (.xlsx) four-tab performance reports." | No PDF capability is scoped, specified, scheduled, or implemented in any revision. The approved reporting deliverable is the four-tab .xlsx workbook defined in §4.2.2. Retaining the PDF promise creates an unfulfillable contractual obligation and is the first item in the de-scoping order should schedule pressure arise. |
| §1.1 | "Multi-Device Data Sync: Provide post-event data transfer mechanisms (Local Wi-Fi Hotspot Sync, Direct USB Import, or Excel/CSV file import) to merge tablet order logs into the primary database." | Replace with: "Multi-Mechanism Data Ingestion: Provide real-time local-LAN order ingestion during events (Mechanism 1), with an offline client transaction queue and USB recovery-package transfer as a fail-safe (Mechanism 2), and manual Excel/CSV batch ingestion as an administrative fallback (Mechanism 3)." | The existing text describes only post-event reconciliation and is contradicted by the ratified architecture, which ingests orders in real time over the local area network. A LAN POST consumes no WAN bandwidth and is therefore fully consistent with the offline-first requirement. |
| New §1.4 | (absent) | Add: "Host Dependency Disclosure: The Industry Client acknowledges that VenueVue operates as a locally networked system in which the host laptop functions as the single authoritative server, and that loss of the host during an event suspends system operation. The Industry Client agrees to maintain a secondary paper fallback procedure for host failure, as provided in Project Plan §2.2.3." | The system has a documented single point of failure. Disclosing it contractually protects both parties and ensures the client maintains the operational fallback that the May 2026 Project Technical Documentation already contemplates. |
| §1.3 | "Database Backup Utility: Build local daily database export capabilities (`.sql` files and external USB exports)…" | Restore the automated backup requirement to the Project Plan. No amendment to the Agreement text is required; rather, NFR-04 has been restored to this Project Plan to match the Agreement. | The automated daily backup requirement was deleted from the plan in a prior revision while the Agreement continued to promise it. Revision 2.3 restores NFR-04 and assigns it to a named owner in Sprint 8 (task 8.6). |
| §3.1.3 | "Provide complimentary bug fixing and system maintenance for a period of six (6) months following official system turnover." | Append: "Support comprises remediation of defects in delivered functionality at no charge. New feature requests fall outside the scope of this Agreement and require separate written agreement." | Bounds the support obligation. The six-month window previously had no owner, no effort allocation, and no scope boundary, creating an open-ended commitment. Task 10.7 now assigns the window to a named owner. |

### 6.2.2 Scope Boundaries

In Scope. The following capabilities constitute the contractual and academic scope of VenueVue Revision 2.3:

1. User authentication with API-level role-based access control across all devices.

2. Touch-optimised POS ordering interface with category tab filtering and single-tap item selection.

3. Real-time cart handling with automatic cash change calculation.

4. Server-side authoritative price resolution.

5. Atomic recipe-based multi-ingredient depletion under row-level locking.

6. Ingredient-level inventory tracking in grams, millilitres, and discrete units.

7. Recipe setup engine mapping raw materials to menu items.

8. Automated low-stock visual alerting with configurable thresholds and a restock list.

9. UUIDv4 idempotency guaranteeing exactly-once transaction ingestion.

10. Multi-mechanism data ingestion: real-time LAN POST, IndexedDB queue with USB recovery, and manual Excel/CSV batch import.

11. Event management and per-event profitability analytics, including event name, venue, date, duration, gross revenue, cost of goods sold, and net profit.

12. Automated generation of four-tab Excel workbooks via PhpSpreadsheet.

13. Automated daily .sql database backup with USB mirroring.

14. Append-only inventory movement ledger and security audit trail.

15. The nine-table relational database schema.

Out of Scope. The following are expressly excluded and will not be delivered:

| Excluded Item | Justification |
| --- | --- |
| Physical receipt printing | TravelBean MNL event customers do not request printed receipts. |
| PDF report export | Not specified, scheduled, or implemented in any revision; struck from the Letter of Agreement by §6.2.1. |
| Online cloud synchronisation | Excluded by ADR-001; the system's defining purpose is independence from cloud infrastructure. |
| Any hosted database or managed authentication provider | Excluded by ADR-001 §2.1.1 and §2.2.4. |
| Hardware barcode scanning | Coffee menu items are selected directly through a touchscreen grid. |
| Customer loyalty programmes | Not applicable to a cash-only, single-event pop-up operation. |
| Integrated e-wallet payment processing | The client operates on a cash-only basis; payment_method is constrained to cash. |
| Simultaneous multi-venue cloud synchronisation | The client operates one event at a time. |
| Kitchen display and order-preparation workflow states | Not applicable to a mobile coffee stand. |
| Supplier, purchase-order, or goods-received-note management | Outside the client's stated operating model. |
| Shift management, cash-drawer reconciliation, and Z-readings | Not requested by the client. |
| Native mobile applications | Retired by ADR-001. |
| Item modifiers or size variants | Not modelled in any approved schema; FR-02's historical reference to "item options" is withdrawn. If size or add-on variants are required, a modifiers table must be added by formal scope change. |
| Tax or VAT computation | Not applicable to the client's current registration status. |

### 6.2.3 Data Privacy Act Compliance (Republic Act No. 10173)

Letter of Agreement §5.1 commits both parties to adherence to the Data Privacy Act of 2012. Revision 2.3 specifies the concrete technical controls that discharge that commitment.

| Control | Implementation | Verification |
| --- | --- | --- |
| Credential protection | Passwords are stored exclusively as password_hash() output with PASSWORD_DEFAULT (bcrypt). No plaintext or reversibly-encrypted credential is ever persisted. Authentication uses password_verify(). | Schema inspection at G2; code review at G4. |
| Session token protection | Only the SHA-256 hash of each bearer token is stored in api_sessions. A database disclosure therefore yields no usable session credential. Tokens carry explicit expiry. | Code review at G4; SELECT against api_sessions confirms hash-only storage. |
| Access control | API-level RBAC enforced server-side on every request. UI-level button hiding is treated as a user-experience feature and never as an authorization control. Unauthorized requests receive HTTP 401 or HTTP 403 and are logged. | Scenarios T10 and T11 at G9. |
| Injection prevention | All database access uses PDO prepared statements with PDO::ATTR_EMULATE_PREPARES => false, guaranteeing genuine server-side preparation. | Code review; static inspection of every query at G4. |
| Audit trail | Every authentication outcome, authorization denial, administrative override, and committed transaction is written to the append-only audit_logs table with acting user, action, entity, structured detail, and client IP address. | Schema and code review; audit_logs population verified at G6. |
| Data minimisation | The system stores only operational data required for POS and inventory functions: no customer names, contact details, payment-card data, or other personal information is captured. Payment is cash-only and no payment instrument is recorded. | Schema inspection at G2; confirms absence of any personal-data column. |
| Data localisation | All data resides on the client's host laptop within the client's premises. No data is transmitted to any third party, and no hosted service is permitted by ADR-001. | WAN-traffic monitoring during a full sales cycle at every gate. |
| Credential hygiene | No credential, connection string, or token is committed to version control. The application connects using a least-privilege database account granted SELECT, INSERT, and UPDATE only — with no DELETE and no DROP privilege. | Repository inspection at G4; SHOW GRANTS at G10. |
| Backup protection | Automated daily .sql dumps are retained on the host drive and mirrored to an external USB drive kept separately from the laptop. | Backup presence verification at G8 and weekly thereafter. |
| Breach remediation | The .env file previously committed to a public repository is removed from version control and its publishable credential rotated, so the historical commit is rendered worthless. Demonstration accounts with known passwords are purged. | Repository and provider-console inspection; recorded as a gate condition at G4. |

### 6.2.4 Intellectual Property and Academic Rights

Letter of Agreement §4 is confirmed without amendment. Under the Intellectual Property Code of the Philippines (Republic Act No. 8293) and Cavite State University academic guidelines:

1. Source code ownership. CTRL + STAY retains full legal ownership, copyright, and intellectual property rights over the source code, system architecture, database structure, and original interface design of VenueVue.

2. Academic presentation rights. CTRL + STAY and Cavite State University reserve the right to demonstrate the system, publish non-confidential screenshots, present methodologies, and submit findings for academic defences, competitions, research journals, and institutional archives.

3. Client data ownership. All operational data, sales figures, inventory records, and transactional records generated through TravelBean MNL's use of VenueVue remain the exclusive property of TravelBean MNL.

4. Third-party components. All third-party libraries used — React, TanStack Router, Vite, Tailwind CSS, PHP, MySQL, XAMPP, and PhpSpreadsheet — are used under their respective open-source licences. No proprietary or licence-encumbered component is introduced.

### 6.2.5 Governing Law

This Project Plan and the Letter of Agreement it supports are governed by, construed, and enforced in accordance with the laws of the Republic of the Philippines, including the Civil Code of the Philippines (R.A. 386), the Intellectual Property Code (R.A. 8293), and the Data Privacy Act of 2012 (R.A. 10173).

# SECTION 7 — APPENDICES

## 7.1 Appendix I — ADR-001 Architecture Decision Record

### ADR-001 — Ratification of the React 19 SPA Client and MySQL/XAMPP Data Tier

| Attribute | Value |
| --- | --- |
| Status | Accepted |
| Date | 23 September 2026 |
| Decision Owner | Zapico, Zaki — Project Manager / Lead Developer |
| Supersedes | Flutter/SQLite client architecture; hosted cloud data tier |
| Related Documents | Project Plan Rev 2.3 §2.1, §2.2, §3.2; System Architecture & Technical Specifications §3.4; Letter of Agreement §1.1 |

#### Context

At the time of the comprehensive document and code audit, three client implementations existed simultaneously in the working environment: two independent Flutter applications using local SQLite persistence, and one React 19 single-page application. The project baseline specified a React 19 SPA served from the host laptop's XAMPP stack against MySQL 8.x, with IndexedDB used only as a client-side transaction queue.

Both Flutter implementations failed their own acceptance criteria. Neither could transmit a payload that the PHP backend would accept, because both posted a flat order map while the backend required a nested {"order": {…}} envelope, and neither ever transmitted the items array the backend required. The larger of the two additionally failed to launch, because it did not register its state-management provider at the application root while its screens requested that provider. It further wrote line items against a literal order identifier of zero without awaiting the database insert, orphaning every line item, and contained a 191-line checkout implementation that was never imported.

The React application carried an undocumented dependency on Supabase — hosted PostgreSQL with GoTrue authentication, accessed over the public internet. The word "Supabase" appears in none of the fourteen project documents. That application contained no PHP, no MySQL, no Apache, and no local-area-network code.

#### Decision

The React 19 / TanStack Router / Vite 8 / Tailwind CSS 4 client, served locally by Apache on the host laptop and persisting to MySQL 8.x through PHP 8.x PDO APIs, is hereby ratified as the sole implementation path for VenueVue.

Both Flutter codebases are frozen and moved to the archive/flutter-prototype branch. They are retained solely as interface design references and receive no further development, feature work, or defect remediation.

The Supabase dependency in the React implementation is removed during Sprint 4 and replaced by the local PHP API specified in Project Plan §4.

#### Rationale

1. Single-source updating. Deploying a rebuilt dist/ folder onto the host laptop updates the entire application across all barista and administrative tablets simultaneously upon browser refresh. Flutter requires manual side-loading on every tablet, and emergency code patches require physical USB access to each device — an impractical operational burden during fast-paced event setups.

2. Universal tablet compatibility. Chrome and Safari both reach the React SPA. Flutter introduces build and OS-version divergence across the client's mixed Android and iPadOS device pool, requiring per-platform artefacts and per-platform testing.

3. Single authoritative store. MySQL 8.x on the host laptop is the sole system of record. A per-tablet SQLite database would create N divergent data stores requiring manual reconciliation — which is precisely the manual labour VenueVue exists to eliminate — and would place inventory truth on devices that can be lost, stolen, or left unsynchronised.

4. Contractual alignment. Letter of Agreement §1.1 specifies "a standalone local server environment (PHP/MySQL) running on a primary laptop workstation that creates a local Wi-Fi hotspot for mobile tablet endpoints." The ratified stack satisfies that specification directly; a Flutter client with per-device SQLite does not, because it relocates authoritative data onto the tablets.

5. Effort feasibility. The approved 650-hour budget across three developers assumes a single implementation. With three implementations in flight, the budget is not attainable and no artefact reaches completion. This is the primary measurable root cause of the project's assessed 12–15% completion against a 38% elapsed timeline.

#### Correction to the Historical Record

Revision 2.0 of the Project Plan asserted that "native mobile builds (such as Flutter APKs) were evaluated during early planning." This claim is not supported by the earliest artefact: the Software Engineering I plan (Rev 3.0, 9 May 2026) contains no reference to Flutter and selected a browser-delivered HTML5/CSS3/JavaScript client.

The accurate historical sequence, which replaces the earlier narrative in all VenueVue documentation, is as follows:

The project's initial architecture was a browser-delivered HTML5/CSS3/JavaScript client. During Revision 2.0 planning, the team evaluated native Flutter APK deployment and rejected it for the operational reasons recorded above — manual side-loading, cross-platform build divergence, and physical USB access required for emergency patches. A React 19 Single Page Application compiled with Vite 8 and styled with Tailwind CSS 4 was selected in its place.

This correction is material because the earlier narrative invited a legitimate challenge from an academic evaluator: a rejected-technology rationale cannot rest on an evaluation that the project's own earliest document does not record.

#### Consequences

Positive. Single-source deployment across all tablets; elimination of per-platform build management; a single authoritative data store with no reconciliation requirement; alignment with the signed Letter of Agreement; and an attainable effort budget.

Negative. The system acquires a documented single point of failure in the host laptop, which is disclosed contractually by the amendment to Letter of Agreement §1.4 and managed operationally by the failure-state definitions in Project Plan §2.2.2 and the recovery procedures in §2.2.3.

Retired capabilities. The sqflite dependency and both database_helper.dart implementations are retired. Client-side durability becomes the responsibility of the IndexedDB queue specified in Project Plan §2.3.4.

Terminology consequence. The term "offline" throughout all VenueVue documentation denotes the absence of WAN/Internet connectivity, not autonomous operation of individual tablets. All documentation, source-code commentary, and oral defence must use this definition.

#### Binding Cloud Exclusion

No hosted database, managed authentication provider, content delivery network, or third-party cloud service shall be introduced into any build of VenueVue.

The Rationale clause of Project Plan §1.2.1 establishes that cloud-dependent POS systems are unusable at TravelBean MNL's venues. Any dependency on a hosted backend falsifies the project's central premise, breaches Letter of Agreement §1.1, introduces undisclosed third-party data processing under R.A. 10173, and cannot be demonstrated at an off-grid event venue.

Compliance is verified at every phase gate by executing a complete sales cycle while monitoring outbound network traffic. The gate passes only on observing zero outbound WAN calls during the cycle. Compliance is additionally evidenced by the absence of any cloud SDK in the build manifest and by an explicit deployment-environment review at gate G10.

#### Protected Scope Consequence

The schema frozen in Revision 2.2 could not deliver the client's headline requirement. Revision 2.3 expands the core schema to nine tables by adding EVENTS, ORDERS.event_id, ORDERS.payment_method, and INGREDIENTS.unit_cost — the minimum required to produce Tab 1 of the contractual workbook, which specifies "Event Name, Date, Duration … Net Profit Estimates … Primary Payment Distribution." The standardised terminology entry "Six-table database → Eight-table core database" is amended to "→ Nine-table core database."

## 7.2 Appendix II — Addendum A: Clarification of Team Role Designations

### ADDENDUM A — Clarification of Team Role Designations

To the Letter of Agreement for College Software Project between CTRL + STAY and TRAVELBEAN MNL

Project: VenueVue: An Internet-Independent Point-of-Sale and Recipe-Driven Inventory Management System

Date of Execution: ____________________

The Parties acknowledge that the role labels recorded on the signature page of the Letter of Agreement do not correspond to the role designations stated in Project Plan Revision 2.3 §1.3.2. The signature page designates Jenny Lyn Roquid as "Developer / System Analyst" and Rhea Mae Gregorio as "Developer / Documenter." Project Plan Revision 2.3 designates Rhea Mae Gregorio as "System Analyst / QA Lead" and Jenny Lyn Roquid as "QA & Testing Specialist."

The Parties further acknowledge that an earlier plan revision contradicted itself on this point, assigning the System Analyst designation to one member on its cover page and to the other in its responsibility table.

To remove all ambiguity for the purposes of the Agreement, academic assessment, and oral defence, the Parties agree that the following designations are authoritative for all purposes under the Letter of Agreement:

| Member | Authoritative Role Designation | Principal Responsibilities |
| --- | --- | --- |
| Zapico, Zaki | Project Manager / Lead Developer | Overall project governance and timeline tracking; client requirements alignment; SWOT prioritisation and risk management; architecture ratification; network topology; database schema design and execution; PHP 8.x backend and API engine; React 19 SPA client architecture; deployment configuration; post-turnover support. |
| Gregorio, Rhea Mae | System Analyst / QA Lead | Requirements gathering and Software Requirements Specification authorship; use-case modelling; ERD and schema design; system architecture documentation; test strategy and test-plan authorship; QA oversight and gate sign-off; master-data CRUD; Figma wireframing; operational manual and installation guide. |
| Roquid, Jenny Lyn | QA & Testing Specialist | Test script execution across scenarios T01–T14; unit, integration, partition, and reconciliation testing; reporting-module validation; low-stock alerting implementation; CSV and USB ingestion verification; IndexedDB quota handling; defect logging; usability assessment; User Acceptance Testing execution; client training delivery. |

Independent verification undertaking. The Parties further record that, to preserve the integrity of quality assurance, no member of CTRL + STAY shall be the sole author and sole verifier of the same deliverable. Every deliverable enumerated in Project Plan §1.2.5 shall carry, at minimum, one named verifier who did not author it. The responsible and verifying parties for each deliverable are specified in the RACI matrix at Project Plan §1.3.3. This undertaking responds directly to a condition identified during audit, in which a single member both constructed and validated the low-stock alerting and reporting modules, and in which the System Analyst both authored and self-signed as reviewer of the same document.

No other amendment. All other terms and conditions of the Letter of Agreement remain in full force and effect and are hereby ratified and confirmed.

FOR THE STUDENT DEVELOPERS — CTRL + STAY

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| ZAKI ZAPICO | Project Manager / Lead Developer | ____________________ | __________ |
| RHEA MAE GREGORIO | System Analyst / QA Lead | ____________________ | __________ |
| JENNY LYN ROQUID | QA & Testing Specialist | ____________________ | __________ |

ACADEMIC ENDORSEMENT

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Faculty Adviser / Project Representative | Department of Computer Studies / IT, CEIT | ____________________ | __________ |

FOR THE INDUSTRY CLIENT — TRAVELBEAN MNL

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| RHONA MAE AGANAN | Owner / Authorized Representative | ____________________ | __________ |
| JIMWELL MAMANGUN | Co-Owner / Operations Manager | ____________________ | __________ |

## APPENDIX III — GLOSSARY AND STANDARDISED TERMINOLOGY

The following terminology is normative. All VenueVue documentation, source-code commentary, presentation material, and oral defence shall use the standardised technical term in the right-hand column.

| Discouraged Formulation | Standardised Technical Term |
| --- | --- |
| "100% fully autonomous tablet" | Internet-independent, locally networked system |
| "100% offline on every tablet" | Offline-first client with local transaction queueing |
| "Three synchronization protocols" | Three data-ingestion mechanisms |
| "Wi-Fi synchronization" | Real-Time Wi-Fi HTTP POST (Mechanism 1) |
| "USB synchronization" | IndexedDB / USB Recovery Import (Mechanism 2) |
| "Excel synchronization" | Manual Excel/CSV Batch Ingestion (Mechanism 3) |
| "Tablet database authority" | Host MySQL database as single authoritative store |
| "Duplicate prevention by order number" | UUIDv4 client transaction ID with database uniqueness constraint |
| "Six-table database" / "Eight-table database" | Nine-table core database |
| "RBAC UI restriction" | PHP API-level authorization enforcement |
| "Synchronization" | Data ingestion |
| "Cloud backup" | Local .sql dump with USB mirror |

## APPENDIX IV — REFERENCES

Industry and Technology Sources

[1] Lavu, "Why Cloud-Based POS is the Future of Restaurant Management." [Online]. Available: https://lavu.com/software-as-a-service-pos/

[2] IBM, "What Is Three-Tier Architecture?" IBM Think. [Online]. Available: https://www.ibm.com/think/topics/three-tier-architecture

[3] Atlassian, "RACI Chart: What is it & How to Use," Atlassian Work Management. [Online]. Available: https://www.atlassian.com/work-management/project-management/raci-chart

[4] Monterail, "How ISO 25010 Frameworks Reduce Technical Debt in Long-Term Projects." [Online]. Available: https://www.monterail.com/blog/software-qa-standards-iso-25010

[5] Dataintelo, "Philippines Coffee Market Research Report 2034." [Online]. Available: https://dataintelo.com/report/philippines-coffee-market

[6] Deepbeez, "Philippines Coffee Industry: Market Size, Growth Forecast 2025." [Online]. Available: https://blog.deepbeez.com/philippines-coffee-industry/

[7] W3C Web Accessibility Initiative, "Notes on User Centered Design Process (UCD)." [Online]. Available: https://www.w3.org/WAI/redesign/ucd

[8] Lavu, "Restaurant POS System Explained: Features, Benefits & Costs in 2025." [Online]. Available: https://lavu.com/what-is-a-pos-system-for-a-restaurant/

[9] OWASP Foundation, "SQL Injection Prevention Cheat Sheet," OWASP Cheat Sheet Series. [Online]. Available: https://cheatsheetseries.owasp.org/cheatsheets/SQL_Injection_Prevention_Cheat_Sheet.html

[10] PHPOffice, "PhpSpreadsheet: A pure PHP library for reading and writing spreadsheet files," GitHub repository. [Online]. Available: https://github.com/PHPOffice/PhpSpreadsheet

[11] Philippine Coffee Board. [Online]. Available: https://philcoffeeboard.com/philippine-coffee/

[12] Tatler Asia, "Can Philippine coffee scale up without leaving farmers behind?" [Online]. Available: https://www.tatlerasia.com/power-purpose/impact/philippine-coffee-industry-evolution

[13] Philippine Coffee Board, "How Philippine Coffee Can Compete in the Global Stage." [Online]. Available: https://philcoffeeboard.com/how-philippine-coffee-can-compete-in-the-global-stage/

[14] digabloPos, "Free Retail POS Software | digabloPos." [Online]. Available: https://digablopos.fr/en/use-cases/retail

[15] digabloPos — Free APK Download for Android, AppBrain. [Online]. Available: https://www.appbrain.com/app/digablopos/com.digablo.pos

[16] Peddlr, "Free POS Inventory Philippines: Download for Sari-Sari Stores," Peddlr Blog. [Online]. Available: https://www.peddlr.io/blog/post/free-pos-inventory-philippines-download-for-sari-sari-stores

[17] digabloPos, "Download digabloPos." [Online]. Available: https://digablopos.fr/en/download

[18] digabloPos, "Android POS: Turn a Smartphone or Tablet Into a Cash Register." [Online]. Available: https://digablopos.fr/en/blog/android-pos-turn-smartphone-or-tablet

[19] digabloPos, "Free POS Software Southeast Asia: Thailand, Vietnam." [Online]. Available: https://digablopos.com/en/regions/asie-du-sud-est

[20] Scribd, "ISO/IEC 25010 Software Quality Model." [Online]. Available: https://www.scribd.com/document/385648250/08-Quality-25010-II-pdf

Technical Standards and Platform Documentation

[21] Oracle Corporation, "MySQL 8.0 Reference Manual — InnoDB Storage Engine, Locking Reads (SELECT ... FOR UPDATE)." [Online]. Available: https://dev.mysql.com/doc/refman/8.0/en/innodb-locking-reads.html

[22] The PHP Group, "PHP Data Objects (PDO) — Prepared Statements and rowCount()." [Online]. Available: https://www.php.net/manual/en/book.pdo.php

[23] The PHP Group, "PHP Password Hashing Functions (password_hash, password_verify)." [Online]. Available: https://www.php.net/manual/en/book.password.php

[24] W3C, "Indexed Database API 3.0," W3C Recommendation. [Online]. Available: https://www.w3.org/TR/IndexedDB/

[25] W3C, "Secure Contexts," W3C Candidate Recommendation. [Online]. Available: https://www.w3.org/TR/secure-contexts/

[26] Meta Open Source, "React 19 Documentation." [Online]. Available: https://react.dev/

[27] TanStack, "TanStack Router Documentation." [Online]. Available: https://tanstack.com/router

Statutory Instruments

[28] Republic Act No. 10173, "Data Privacy Act of 2012," Republic of the Philippines.

[29] Republic Act No. 8293, "Intellectual Property Code of the Philippines," Republic of the Philippines.

[30] Republic Act No. 386, "Civil Code of the Philippines," Republic of the Philippines.

## DOCUMENT APPROVAL AND SIGN-OFF

This Project Plan, Document Revision 2.3 (Final Architecture-Reconciled & Audit-Aligned Baseline), is submitted for approval and adoption as the governing management instrument for the VenueVue project.

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Manager / Lead Developer | ZAPICO, ZAKI | ____________________ | __________ |
| System Analyst / QA Lead | GREGORIO, RHEA MAE | ____________________ | __________ |
| QA & Testing Specialist | ROQUID, JENNY LYN | ____________________ | __________ |
| Industry Client — Owner / Operations Manager | AGANAN, RHONA MAE | ____________________ | __________ |
| Industry Client — Co-Owner / Logistics Manager | MAMANGUN, JIMWELL | ____________________ | __________ |
| Academic Instructor / Evaluator | ____________________ | ____________________ | __________ |

Document Classification: Academic — Cavite State University, College of Engineering and Information Technology, Department of Computer Studies / Information Technology

End of Document — VenueVue Project Plan, Document Revision 2.3