# Project Plan 2.0 (Revised & Reconciled)

COSC 75: Software Engineering II

VenueVue: Internet-Independent Point-of-Sale and Recipe-Driven Inventory Management System for Mobile Pop-Up Coffee Shops

Client: TravelBean MNL

Document Revision No.: Rev 2.1 (Reconciled & Architecture-Aligned)

Date of Issue: September 23, 2026

Project Manager / Group Members: Zapico, Zaki; Roquid, Jenny Lyn; Gregorio, Rhea Mae

## 1. Executive Summary & Problem Domain

### 1.1 Statement of the Problem

Mobile pop-up coffee ventures operating in temporary venues—such as outdoor fairs, private weddings, school grounds, and corporate events—face operational bottlenecks due to reliance on manual paper sales tracking, post-event calculator sales tallying, and visual inventory estimation. Cloud-dependent Point-of-Sale (POS) systems are unusable in dead zones or congested wireless environments. Existing retail software tracks finished products as discrete units rather than raw materials, leaving operators unable to monitor recipe depletion (e.g., deducting espresso beans in grams, milk in milliliters, and plastic cups in units per beverage sold).

A quantitative SWOT and problem-prioritization analysis conducted by group CTRL+STAY with TravelBean MNL identified seven core operational problems:

| Priority Rank | Problem Identification | Operational Impact | Current Client Workaround | Priority Score |
| --- | --- | --- | --- | --- |
| 1 | Absence of an Internet-independent POS system | Forces paper-based order entry; leads to miscalculated totals and lost order slips. | Writing orders on physical notepads. | 43 |
| 2 | Manual post-event sales tallying | Requires 2–3 hours of manual calculations per event; causes operator burnout. | Tallying paper receipts using handheld calculators. | 42 |
| 3 | Inefficient product & ingredient tracking | Mid-event stockouts of essential items (espresso beans, full-cream milk, cups). | Visual estimation and manual post-event updates to basic Excel sheets. | 38 |
| 4 | Absence of low-stock alert notifications | Staff remain unaware when raw materials hit critical thresholds, causing rejected orders. | Manual spot checks during event lulls. | 34 |
| 5 | Lack of historical event performance data | Management cannot identify best-selling products, peak hours, or high-margin events. | Reliance on gut feeling and basic memory. | N/A |
| 6 | Time-consuming administrative reconciliation | Labor fatigue reduces overall operational efficiency and business scalability. | Owners working long unpaid hours after events. | N/A |
| 7 | Severe manpower constraints | Small team (3 members) divided between customer service and manual paperwork. | Operations Manager personally handling manual logging during sales. | N/A |

### 1.2 System Scope & Operational Availability Definition

VenueVue is an Internet-independent, locally networked, offline-first Point-of-Sale (POS) and recipe-driven inventory management system utilizing an edge host server (Apache/PHP/MySQL) over a local Wi-Fi LAN (192.168.137.x).

Operational Availability Definition: VenueVue guarantees operational availability independent of WAN/Internet access, provided that the local host server and local wireless network remain operational. "Offline" in this study refers specifically to the absence of WAN/Internet connectivity, not complete autonomous operation of each individual tablet. The system relies on the local host server for authoritative transaction processing, recipe inventory computation, RBAC session validation, and database persistence.

### 1.3 Quantifiable Research Objectives & Metrics

The system's technical success is governed by seven measurable objectives mapped to formal experimental metrics:

| # | Specific Objective | Quantifiable Success Metric / Formula | Target Criterion |
| --- | --- | --- | --- |
| 1 | Digitally capture customer transactions. | Paper order elimination rate. | 100% elimination of paper slips during event operations. |
| 2 | Automate raw material inventory deductions based on product recipe mappings. | Recipe Deduction Accuracy ($A_{deduction}$): $$A_{deduction} = \left( 1 - \frac{\sum_{i=1}^{n}\vert Q_{BOM,i}-Q_{DB,i}\vert}{\sum_{i=1}^{n}\vert Q_{BOM,i}\vert} \right) \times 100\%$$ | $A_{deduction} = 100.00\%$ precision between theoretical BOM depletion ($Q_{BOM}$) and database records ($Q_{DB}$). |
| 3 | Implement real-time low-stock alerting. | Alert accuracy rate (True Positive vs. False Positive). | Display visual alerts immediately when $Q_{hand} \le Q_{threshold}$. |
| 4 | Guarantee Internet-independent system availability during mobile events. | WAN-Partitioned Functional Availability. | 100% operational availability during total WAN outages provided local LAN and Host Laptop remain active. |
| 5 | Automate post-event sales and operational report generation. | Export Latency ($T_{export}$): Execution time for 4-tab .xlsx workbook compilation. | $T_{export} \le 10 \text{ seconds}$ post-event via PhpSpreadsheet. |
| 6 | Enable flexible multi-device data ingestion post-event. | Offline Reconciliation Rate ($R_{sync}$): $$R_{sync} = \frac{N_{reconciled}}{N_{queued}} \times 100\%$$ | $R_{sync} = 100\%$ reconciliation, $0\%$ duplicate records ($R_{duplicate} = 0\%$) post-partition. |
| 7 | Enforce API-level Role-Based Access Control (RBAC) across devices. | Authorization enforcement rate on PHP endpoints. | HTTP 403 Forbidden on unauthorized API calls (e.g., Baristas triggering stock edits). |

## 2. Approach & Methodological Framework

The project governs implementation and research evaluation through four distinct methodologies, each assigned a strictly bounded functional role:

METHODOLOGICAL FRAMEWORK
                                 │
     ┌───────────────────────────┼───────────────────────────┐
     ▼                           ▼                           ▼
Waterfall Governance        Agile Scrum                User-Centered         ISO/IEC 25010 Quality
(Academic Stage Gates)  (2-Week Sprints)              Design (UCD)               Model
     │                           │                           │                     │
     ├─ SRS & Documentation      ├─ Iterative Features       ├─ Touch Targets      ├─ Functional Suitability
     ├─ Architecture Freeze      ├─ Sprint Retrospects       ├─ High-Contrast UI   ├─ Operational Reliability
     └─ UAT Sign-off             └─ Code Refactoring         └─ Tap Minimization   └─ Security Benchmarking

- Waterfall Governance (SDLC): Manages academic stage gates, compliance documentation, formal design freezes, and final sign-off checkpoints.

- Agile Scrum: Guides software construction in two-week iterative sprints, enabling continuous feature refinement, bug logging, and incremental testing.

- User-Centered Design (UCD): Governs front-end UI engineering, prioritizing touch-target dimensions, contrast levels, and tap-count minimization for high-volume barista workflows.

- ISO/IEC 25010 Quality Model: Establishes the benchmarking taxonomy for functional suitability, operational reliability, performance efficiency, and backend security.

## 3. Reconciled System Architecture Specification

VenueVue operates as an edge client-server system deployed over a local wireless star network topology (192.168.137.x).

VENUEVUE
                      INTERNET-INDEPENDENT EDGE POS
                                   │
            ┌──────────────────────┴──────────────────────┐
            │                                             │
       CLIENT TIER                                    EDGE HOST
 (React 19 SPA / PWA)                           (Apache / PHP 8.x)
            │                                             │
    Barista & Admin UI                          Authentication & Session
    IndexedDB Local Queue                       API-Level RBAC Enforcement
            │                                   Idempotency Processing
            │                                   Recipe Deduction Engine
            │                                   Stock Alerting Engine
            │                                   PhpSpreadsheet Export
            │                                             │
            └─────────────── Local Wi-Fi ─────────────────┘
                                   │
                              MySQL 8.x
                           (InnoDB Engine)
                                   │
      ┌───────────┬───────────┬────┴──────┬───────────┬───────────┐
      │           │           │           │           │           │
    USERS     PRODUCTS   INGREDIENTS   RECIPE_     ORDERS      ORDER_
                                        ITEMS                   ITEMS
                                                                  │
                                                          ┌───────┴───────┐
                                                          │               │
                                                     INVENTORY_       AUDIT_LOGS
                                                    TRANSACTIONS

### 3.1 Three-Tier Operational Layers

- Client Tier (Presentation): React 19 SPA / PWA executed on Barista and Admin tablets via standard browsers or standalone Kiosk WebView containers. Handles UI rendering, cart state, local input validation, and an IndexedDB local transaction queue during network interruptions.

- Application Tier (Business Logic): Hosted on the central laptop via XAMPP (Apache / PHP 8.x). Validates sessions, enforces role permissions, executes atomic recipe deductions, handles idempotency checks, and compiles Excel exports.

- Data Tier (Persistence): MySQL 8.x database running on the InnoDB engine. Guarantees ACID-compliant persistence across 8 core relational tables using prepared SQL statements.

### 3.2 Three Data-Ingestion Mechanisms

VenueVue replaces the concept of "three synchronization protocols" with three distinct data-ingestion mechanisms pointing to the authoritative local database:

- Mechanism 1 — Real-Time Wi-Fi HTTP POST (Primary): Client tablets transmit completed transactions directly to the PHP API endpoint over local Wi-Fi (192.168.137.x).

- Mechanism 2 — Local IndexedDB / USB Recovery Import (Fail-Safe): If local Wi-Fi drops, transactions queue in the tablet's IndexedDB in a PENDING_LOCAL state. Queue records can be exported as structured JSON recovery packages and transferred to the host laptop via USB drive.

- Mechanism 3 — Manual Excel/CSV Batch Ingestion (Administrative Fallback): Administrative transaction files uploaded via the Mobile Admin Console are validated, parsed via PhpSpreadsheet, checked for duplicate idempotency keys, and committed atomically.

### 3.3 Offline State Machine & Idempotency Engine

To prevent duplicate orders when Wi-Fi drops mid-checkout, every transaction receives a client-generated UUIDv4 client_transaction_id before transmission.

┌──────────────────┐
                 │  Create Order    │
                 └────────┬─────────┘
                          │
                          ▼
                 ┌──────────────────┐
                 │  PENDING_LOCAL   │ (IndexedDB Cache)
                 └────────┬─────────┘
                          │
                   HTTP POST Attempt
                          │
              ┌───────────┴───────────┐
              │                       │
           Success                 Failure
              │                       │
              ▼                       ▼
       ┌─────────────┐         ┌─────────────┐
       │  COMMITTED  │         │PENDING_LOCAL│
       └─────────────┘         └──────┬──────┘
                                      │
                               Retry / USB Export
                                      │
                                      ▼
                               ┌─────────────┐
                               │  COMMITTED  │
                               └─────────────┘

The database enforces a UNIQUE constraint on ORDERS.client_transaction_id. When the PHP API receives a transaction:

- It checks client_transaction_id against ORDERS.

- If it already exists, the server returns the existing transaction result without re-executing recipe deductions or inserting duplicate records.

- If new, it processes the order atomically and returns 201 Created.

- The client marks the local state as COMMITTED only after receiving the server's HTTP confirmation.

### 3.4 Multi-Tablet Concurrency & Atomic Row Locking

When multiple barista tablets sell items simultaneously, inventory deductions execute inside an atomic InnoDB transaction using row-level locking:

SQL

START TRANSACTION;

-- 1. Lock candidate ingredient rows to prevent concurrent read/write race conditions
SELECT ingredient_id, current_stock 
FROM INGREDIENTS 
WHERE ingredient_id IN (101, 102) 
FOR UPDATE;

-- 2. PHP validates current_stock >= required_quantity
-- 3. Execute deductions
UPDATE INGREDIENTS SET current_stock = current_stock - 18.000 WHERE ingredient_id = 101;
UPDATE INGREDIENTS SET current_stock = current_stock - 200.000 WHERE ingredient_id = 102;

-- 4. Record master order and line items
INSERT INTO ORDERS (client_transaction_id, user_id, tablet_id, total_amount, cash_tendered, created_at, committed_at) 
VALUES ('550e8400-e29b-41d4-a716-446655440000', 2, 'T-01', 340.00, 500.00, NOW(), NOW());

-- 5. Record movement deltas and audit logs
INSERT INTO INVENTORY_TRANSACTIONS (ingredient_id, user_id, order_id, transaction_type, quantity_delta, created_at)
VALUES (101, 2, LAST_INSERT_ID(), 'SALE', -18.000, NOW());

COMMIT;

## 4. Eight-Table Database Schema

The relational database is expanded to eight core tables to ensure complete auditability, inventory movement tracking, and security auditing:

┌───────────────┐
                      │     USERS     │
                      └───────┬───────┘
                              │ 1
                              │ creates / performs
                              ▼ *
   ┌──────────────────────────┴──────────────────────────┐
   │                                                     │
   ▼ *                                                   ▼ *
┌───────────────────────┐                     ┌────────────────────────┐
│        ORDERS         │                     │ INVENTORY_TRANSACTIONS │
└───────────┬───────────┘                     └───────────┬────────────┘
            │ 1                                           │ *
            │ contains                                    │ references
            ▼ *                                           │
┌───────────────────────┐                                 │
│      ORDER_ITEMS      │                                 │
└───────────┬───────────┘                                 │
            │ *                                           │
            │ references                                  │
            ▼ 1                                           │
┌───────────────────────┐                                 │
│       PRODUCTS        │                                 │
└───────────┬───────────┘                                 │
            │ 1                                           │
            │ maps via                                    │
            ▼ *                                           │
┌───────────────────────┐                                 │
│     RECIPE_ITEMS      │                                 │
└───────────┬───────────┘                                 │
            │ *                                           │
            │ targets                                     │
            ▼ 1                                           ▼ 1
┌───────────────────────────────────────────────────────────┐
│                        INGREDIENTS                        │
└─────────────────────────────┬─────────────────────────────┘
                              │ 1
                              │ logged via
                              ▼ *
                      ┌───────────────┐
                      │  AUDIT_LOGS   │
                      └───────────────┘

- USERS: user_id (PK), username (UNIQUE), password_hash, role (ENUM: BARISTA, OWNER), is_active, created_at.

- PRODUCTS: product_id (PK), product_name, category, unit_price, is_active.

- INGREDIENTS: ingredient_id (PK), ingredient_name, unit (g, mL, units), current_stock, minimum_stock, updated_at.

- RECIPE_ITEMS: recipe_item_id (PK), product_id (FK), ingredient_id (FK), quantity_required. Constraint: UNIQUE(product_id, ingredient_id).

- ORDERS: order_id (PK, BIGINT), client_transaction_id (CHAR(36), UNIQUE, NOT NULL), user_id (FK), tablet_id, total_amount, cash_tendered, created_at, committed_at.

- ORDER_ITEMS: order_item_id (PK, BIGINT), order_id (FK), product_id (FK), quantity, unit_price.

- INVENTORY_TRANSACTIONS (New): inventory_transaction_id (PK, BIGINT), ingredient_id (FK), user_id (FK), order_id (Nullable FK), transaction_type (ENUM: SALE, RESTOCK, ADJUSTMENT), quantity_delta, reason, created_at.

- AUDIT_LOGS (New): audit_log_id (PK, BIGINT), user_id (Nullable FK), action, entity_type, entity_id, details (JSON/TEXT), ip_address, created_at.

## 5. Experimental Test Matrix & Traceability

The technical verification of VenueVue follows a 14-scenario experimental test protocol:

| Test ID | Scenario Description | Primary Metric | Expected Condition / Acceptance Criteria |
| --- | --- | --- | --- |
| T01 | Single tablet normal transaction submission | $L_{trans}$ | Successful commit; $L_{trans} \le 250\text{ ms}$ on local LAN. |
| T02 | Two tablets submitting simultaneous sales | Inventory Consistency | Zero lost updates or race conditions; correct sequential atomic commits. |
| T03 | Concurrent sales depleting the same ingredient | $A_{deduction}$ | $A_{deduction} = 100\%$; row-level locks prevent stale stock reads. |
| T04 | Local Wi-Fi disconnect during checkout | System State | Transaction safely retained in tablet IndexedDB as PENDING_LOCAL. |
| T05 | Wi-Fi restoration after network partition | $R_{sync}$ | $R_{sync} = 100\%$; queued transactions automatically reconcile to host. |
| T06 | Timeout during transmit followed by retry | $R_{duplicate}$ | $R_{duplicate} = 0\%$; UUID uniqueness constraint rejects second insert. |
| T07 | Duplicate USB recovery file import | $R_{duplicate}$ | Server identifies existing client_transaction_id and skips re-deduction. |
| T08 | Excel/CSV administrative batch import | Import Success | Valid records committed atomically; malformed rows roll back transaction. |
| T09 | Order placement with insufficient ingredient stock | Transaction Policy | PHP rejects transaction with HTTP 409 Conflict; inventory unaltered. |
| T10 | Barista account triggering stock adjustment API | RBAC Enforcement | PHP API returns HTTP 403 Forbidden; violation logged in AUDIT_LOGS. |
| T11 | Request using expired or invalid session token | Security Validation | PHP API returns HTTP 401 Unauthorized; operation rejected. |
| T12 | Recipe BOM verification across all menu items | $A_{deduction}$ | Calculated recipe quantities exactly match INVENTORY_TRANSACTIONS deltas. |
| T13 | Ingredient stock falling below minimum_stock | Alert Accuracy | Interface renders low-stock badge; item logged in Restock List. |
| T14 | Automated 4-tab Excel workbook generation | $T_{export}$ | Multi-tab .xlsx workbook compiled and downloaded in $T_{export} \le 10\text{ s}$. |

## 6. Project Timeline & Task Tracker

Academic Timeline: August 3, 2026 – December 18, 2026 (20 Weeks)

Current Milestone: Phase 1 Milestone (20% Completed) as of September 22, 2026.

+-----------------------------------------------------------------------------------+
| AUG 2026             SEP 2026             OCT 2026             NOV 2026  DEC 2026|
| [--- PHASE 1 ---]                                                                 |
| (Requirements & Architecture - 20% MILESTONE COMPLETED)                           |
|                      [--- PHASE 2 ---]                                            |
|                      (UI Design, 8-Table ERD & React Setup - IN PROGRESS)         |
|                                           [-------- PHASE 3 --------]             |
|                                           (Core Development & Integration)        |
|                                                                [-- P4 --]         |
|                                                                (Testing)          |
|                                                                          [--P5--] |
|                                                                          (Deploy) |
+-----------------------------------------------------------------------------------+

### 6.1 Work Breakdown Structure (WBS)

| Phase / Module | Task / Feature Description | Tech Component | Assigned Owner | Status | Target Date | Dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Requirement Analysis & SWOT Analysis | Research Docs | Z. Zapico | Completed | Aug 14, 2026 | None |
| Phase 1 | System Architecture & Network Design | Tech Specs | R. Gregorio | Completed | Aug 21, 2026 | Requirements |
| Phase 1 | 8-Table Database DDL & Schema Setup | MySQL 8.x / PHP | Z. Zapico | Completed | Aug 28, 2026 | Architecture |
| Phase 2 | UI Design Tokens & React 19 SPA Setup | Vite 8 / Tailwind 4 | R. Gregorio | Completed | Sep 04, 2026 | Schema Setup |
| Phase 2 | Auth Routing & Navigation Flows | TanStack Router | Z. Zapico | In Progress | Sep 18, 2026 | Design Tokens |
| Phase 2 | Figma Touch UI Wireframes (7 Screens) | Figma | R. Gregorio | Pending | Sep 25, 2026 | Auth Routing |
| Phase 3 | Touch POS Interface & Cart Engine | React 19 / Tailwind | Z. Zapico | Pending | Oct 09, 2026 | Figma UI |
| Phase 3 | Atomic Recipe Deduction Engine | PHP 8.x / PDO | Z. Zapico | Pending | Oct 23, 2026 | POS Interface |
| Phase 3 | Low-Stock Visual Alerting Module | React 19 / PHP | J. Roquid | Pending | Oct 30, 2026 | Recipe Engine |
| Phase 3 | Ingestion Engine & UUID Idempotency | PHP 8.x / Hotspot | Z. Zapico | Pending | Nov 06, 2026 | Stock Alerts |
| Phase 3 | PhpSpreadsheet 4-Tab Export Engine | PhpSpreadsheet | J. Roquid | Pending | Nov 20, 2026 | Ingestion Engine |
| Phase 4 | Partition & Fail-Safe Stress Testing | Local LAN / USB | J. Roquid | Pending | Nov 27, 2026 | Export Engine |
| Phase 4 | Integration & Bug Fixing Cycle | Issue Tracker | R. Gregorio | Pending | Dec 04, 2026 | Stress Testing |
| Phase 5 | Production Hardware Setup & Hotspot Config | Local Host Server | Z. Zapico | Pending | Dec 11, 2026 | Bug Fixing |
| Phase 5 | UAT Sign-Off & Thesis Documentation | UAT Certificate | Team CTRL+STAY | Pending | Dec 18, 2026 | Hardware Setup |

## 7. Budget Allocation

### 7.1 Financial & Labor Valuation

- Software Licensing: ₱0.00 (All software layers—React 19, Vite 8, Tailwind CSS 4, PHP 8.x, MySQL 8.x, XAMPP, PhpSpreadsheet—operate under open-source licenses).

- Hardware & Media Outlays: ₱900.00 (Two high-speed 64GB USB flash drives for secondary offline database backups).

- Operational & Deployment Outlays: ₱10,700.00 (Client site travel to Tondo, Manila, testing supplies, printing, and contingency).

- Software Engineering Labor Valuation (650 Total Hours):

  - Z. Zapico (250 hrs @ ₱250/hr = ₱62,500.00)

  - R. Gregorio (220 hrs @ ₱200/hr = ₱44,000.00)

  - J. Roquid (180 hrs @ ₱180/hr = ₱32,400.00)

  - Imputed Labor Total: ₱138,900.00

### 7.2 Total Projected Budget Summary

| Budget Allocation Category | Direct Out-of-Pocket Cost (PHP) | Imputed Project Valuation (PHP) |
| --- | --- | --- |
| Software Licenses | ₱0.00 | ₱0.00 |
| Hardware & Storage Media | ₱900.00 | ₱33,900.00 (Includes Client Hardware) |
| Software Engineering Labor (CTRL+STAY) | ₱0.00 | ₱138,900.00 |
| Operational & Deployment Outlays | ₱10,700.00 | ₱10,700.00 |
| TOTAL PROJECTED EXPENDITURE | ₱11,600.00 | ₱183,500.00 |

## 8. Final Terminology Standard

To ensure academic rigor across the thesis, project plan, source code comments, and oral defense, the following terminology standards are strictly enforced:

| Avoid Unclear Term | Standardized Technical Term |
| --- | --- |
| "100% fully autonomous tablet" | Internet-independent, locally networked system |
| "100% offline on every tablet" | Offline-first client with local transaction queueing |
| "Three synchronization protocols" | Three data-ingestion mechanisms |
| "Wi-Fi synchronization" | Real-Time Wi-Fi HTTP POST |
| "USB synchronization" | IndexedDB / USB Recovery Import |
| "Excel synchronization" | Manual Excel/CSV Batch Ingestion |
| "Tablet database authority" | Host MySQL database as single authoritative store |
| "Duplicate prevention by order number" | UUIDv4 client transaction ID + Database uniqueness constraint |
| "Six-table database" | Eight-table core database |
| "RBAC UI restriction" | PHP API-level authorization enforcement |